## Team Directory
WITYLOGIX — STARTUP ENGINEERING TEAM
9-person team organized into 5 squads — working in parallel across 6 phases
ID | Name | Role | Squad | Focus Areas | Parallel Tracks | Models | Pages | Services | Infra | Roadmap | Total Items
AR | Arjun Rajput | CTO / Tech Lead | Architecture | System design, API architecture, DB schema, auth, infra decisions | Auth system, RBAC, schema design, code reviews | 6 | 1 | 6 | 2 | 3 | 18
PK | Priya Kapoor | Sr. Backend Engineer | Core Backend | Order/shipment lifecycle, business logic, Shopify sync, webhooks | Order CRUD, shipment model, webhook processors, Shopify sync engine | 8 | 0 | 10 | 1 | 9 | 28
VS | Vikram Shah | Backend Engineer | Core Backend | Route optimization, geospatial, carrier service, location mgmt | PostGIS, route optimization, shipping profiles, delivery rules, carrier rates | 6 | 1 | 12 | 0 | 5 | 24
NK | Neha Krishnan | Sr. Frontend Engineer | Frontend | Dashboard UI, design system, pages, components, UX | Design system, dashboard pages, settings, analytics, onboarding | 1 | 15 | 0 | 0 | 1 | 17
DM | Dev Malhotra | Frontend Engineer | Frontend | Order/shipment/route pages, map integrations, forms | Order pages, shipment pages, route create/edit, zone map drawing, forms | 0 | 15 | 0 | 1 | 3 | 19
SP | Sanya Patel | Full-Stack Engineer | Integrations | Notification providers, email/SMS/WhatsApp, Firebase push, templates | SendGrid, Twilio, WhatsApp, FCM, notification templates, campaign system | 7 | 3 | 7 | 4 | 6 | 27
RG | Rohan Gupta | Full-Stack Engineer | Integrations | Payment gateways, billing, analytics, 3rd-party APIs, super admin | Payment module, billing/plans, analytics engine, cart plugin, POS | 9 | 4 | 10 | 1 | 5 | 29
AM | Aisha Mehra | DevOps / Infra Engineer | Platform | Docker, CI/CD, Redis, BullMQ, PostGIS, monitoring, deployment | Queue infrastructure, Redis caching, PostGIS setup, Docker, CI/CD, logging | 6 | 0 | 8 | 13 | 7 | 34
KS | Kabir Singh | QA / Test Engineer | Quality | Test strategy, E2E tests, API tests, regression, data migration QA | Test framework setup, API test suites, E2E scenarios, migration validation | 0 | 0 | 0 | 1 | 0 | 1
TOTAL | [5 empty] | 43 | 39 | 53 | 23 | 39 | 197
Squad Structure
Squad | Members | Primary Responsibility | Phase Focus
Architecture | AR (Arjun) | System design, auth, schema, cross-cutting concerns, code reviews | Phase 1 lead, oversight all phases
Core Backend | PK (Priya), VS (Vikram) | Order lifecycle, shipments, routes, shipping profiles, Shopify sync | Phase 1-2 primary, Phase 4 support
Frontend | NK (Neha), DM (Dev) | Dashboard UI, all pages, design system, map integrations, UX | Phase 1-2 primary (parallel with backend)
Integrations | SP (Sanya), RG (Rohan) | Notifications, payments, billing, analytics, 3rd-party APIs | Phase 3-4 primary, Phase 5-6
Platform | AM (Aisha) | Infrastructure, DevOps, queues, caching, monitoring, deployment | Phase 1 setup, continuous throughout
Quality | KS (Kabir) | Test strategy, automation, E2E, API tests, migration validation | Continuous from Phase 2 onwards

## Executive Summary
WITYLOGIX PLATFORM — GAP ANALYSIS
Old Backend (lmd-oms-v3 + lmd-oms-nextjs-v3) → New Platform (witylogix-platform)
Last Updated: Sprint 2.6 (2026-03-07) | Old System | New Platform | Gap
Total Files: 555 source files ¦ 168,753 lines of code | 38+ | 26 (Prisma) | Consolidated into fewer, richer models
Sprints Completed: 1.1, 1.2, 2.0, 2.1, 2.2, 2.3, 2.4, 2.5 | 68 | 50 | Many features still need pages
API Routes | 85+ (Express) | 42 (Fastify) | Many endpoints still needed
Services/Controllers | 140+ / 80+ | 7+ queue consumers | Core business logic to rebuild
Microservices (PM2) | 12 | 1 monolith + workers | Queue workers needed
Notification Channels | Email, SMS, WhatsApp, Push, Slack | Schema only | All providers to integrate
Payment Systems | COD, Custom Gateways, Shopify Txn | COD + gateway abstractions | Stripe/Razorpay implementation needed
Map Providers | Google Maps + Mapbox | Haversine + PostGIS spatial module | PostGIS extension enable needed
Webhook Processors | 5 dedicated servers | 4 webhook consumers | Additional webhook types needed
Real-time Tracking | Firebase + WebSocket | None | Driver tracking to build
Campaign/Marketing | Email templates, Broadcasts | None | Campaign module needed
Integrations | 38 marketplace providers | Schema + registry | Provider implementations needed
Components | 296+ | ~12 | Component library to expand

## Data Models Gap
Old Model (MongoDB) | Collection | New Model (Prisma) | Status | Key Fields Missing in New | Priority | Notes | Done | Assignee | Squad | Work Status
shopifyOrder | shopify_orders | Order | EXISTS | lineItems detail, billingAddress, shippingAddress, financialStatus, fulfillmentStatus, tags (rich), cancelledAt, refunds, discountCodes, taxLines, shippingLines, noteAttributes, orderRisk, orderSource | P0 | Core model - needs many Shopify-specific fields | ☑ | PK - Priya | Core Backend | DONE
shipment | shipments | Shipment | EXISTS | Entire model: tracking_number, carrier, shipping_method, status lifecycle, label_url, customs_info, insurance, return_tracking, package_dimensions, weight, estimated_delivery_date, actual_delivery_date, shipping_cost, recipient_details, documents[], activity_log[] | P0 | Critical gap - old system had full shipment lifecycle separate from orders | ☑ | PK - Priya | Core Backend | DONE
shipmentItem | shipment_items | ShipmentProof | PARTIAL | Entire model: shipment_ref, product_id, variant_id, quantity, weight, dimensions, customs_value, hs_code, origin_country | P0 | Needed for per-item shipment tracking | ☐ | PK - Priya | Core Backend | IN PROGRESS
user | users | User | EXISTS | phone, avatar, permissions[], timezone, language, lastActiveAt, inviteToken, inviteExpiry, twoFactorEnabled, notificationPreferences | P1 | Old had richer user profiles | ☑ | AR - Arjun | Architecture | DONE
userRole | user_roles | User.role (enum) | EXISTS | Full RBAC model with permissions array, resource-level access, customizable roles | P1 | Old had dynamic roles; new uses fixed enum | ☑ | AR - Arjun | Architecture | DONE
userPermission | user_permissions | — | MISSING | Entire model: role_ref, resource, action, allow/deny, conditions | P1 | Granular permission system missing | ☑ | AR - Arjun | Architecture | DONE
storeDetail | store_details | Shop | EXISTS | address, country, province, logo, favicon, social_links, business_hours, description, industry, defaultLanguage, supportEmail, returnPolicy, trackingPageConfig, widgetConfig, analyticsConfig | P1 | Shop model is minimal vs old storeDetail | ☑ | AR - Arjun | Architecture | DONE
storeSettings | store_settings | Shop.settings (JSON) | EXISTS | Structured settings: autoAssign, proofOfDelivery, signatureRequired, realTimeTracking, driverAppConfig, customerNotificationDefaults, inventorySync, fulfillmentRules | P1 | Old had explicit fields; new uses opaque JSON | ☑ | AR - Arjun | Architecture | DONE
storeApiSettings | store_api_settings | Integration | EXISTS | Old had dedicated model for API keys per provider (Google, Mapbox, Twilio, SendGrid, etc.) | P2 | Subsumed by Integration model but less explicit | ☑ | SP - Sanya | Integrations | DONE
storeInfo | store_infos | Shop | EXISTS | Merged into Shop model | — | Consolidated correctly | ☑ | — | — | DONE
calenderRule / calenderProfile | calender_rules / calender_profiles | — | MISSING | Entire models: blackout_dates[], operating_hours{}, preparation_time, cutoff_rules, holiday_calendars, recurring_rules, capacity_by_day, special_event_overrides | P0 | Sprint 2.5: calendar-engine.ts in shipping-profiles module | ☑ | VS - Vikram | Core Backend | DONE
deliveryRule / pickupRule / shippingRule | Various | — | EXISTS | Entire rule engines: distance-based, weight-based, zone-based, product-category, minimum-order, time-window, same-day/next-day rules, rate tables, conditional logic | P0 | Sprint 2.4 - DeliveryRule, PickupRule, CalendarProfile models added | ☑ | VS - Vikram | Core Backend | DONE
shippingProfile | shipping_profiles | ShippingProfile + ShippingRate + ShippingZoneRule + DeliveryCalendar | MISSING | Entire model: locations[], rates[], rules[], zones[], delivery_methods[], processing_times, conditions, product_groups | P0 | Sprint 2.5: 31-shipping-profiles-v2.prisma + full core module | ☑ | VS - Vikram | Core Backend | DONE
zone | zones | DeliveryZone | EXISTS | boundary polygon (PostGIS), color, description, delivery_methods[], associated_locations[], max_distance, estimated_time_range | P1 | PostGIS boundary is TODO; zone features limited | ☑ | VS - Vikram | Core Backend | DONE
location / warehouse | locations | Location | EXISTS | Entire model: name, address, coordinates, type (warehouse/store/hub), inventory[], working_hours, pickup_rules, delivery_rules, associated_zones[], capacity, contact_info | P0 | No location/warehouse model in new schema | ☑ | VS - Vikram | Core Backend | DONE
vehicle | vehicles | Driver (with vehicle fields) | EXISTS | Old had separate Vehicle model: make, model, year, color, insurance, registration, capacity_volume, capacity_weight, fuel_type, maintenance_schedule | P2 | New schema has vehicleType/vehiclePlate on Driver only | ☑ | VS - Vikram | Core Backend | DONE
notificationTemplate | notification_templates | NotificationTemplate | EXISTS | Entire model: channel, event_type, subject, body_template, variables[], isActive, language, version | P1 | Notification template system missing | ☑ | SP - Sanya | Integrations | DONE
notificationConfig | notification_configs | NotificationLog | EXISTS | Per-store notification preferences: enabled_channels{}, event_subscriptions{}, quiet_hours, frequency_limits | P1 | Notification configuration missing | ☑ | SP - Sanya | Integrations | DONE
whatsappTemplate | whatsapp_templates | — | MISSING | Entire model: template_id, name, language, category, components[], status, provider_template_id | P2 | WhatsApp Business template management | ☑ | SP - Sanya | Integrations | DONE
campaign | campaigns | — | MISSING | Entire model: name, type, audience_filter, template_ref, schedule, status, sent_count, open_rate, click_rate | P2 | Campaign/marketing module missing | ☑ | SP - Sanya | Integrations | DONE
broadcastGroup | broadcast_groups | — | MISSING | Entire model: name, type, member_filter, members[], metadata | P2 | Broadcast targeting missing | ☑ | SP - Sanya | Integrations | DONE
emailTemplate | email_templates | — | MISSING | Entire model: name, subject, html_body, design_json (Unlayer), category, variables[] | P2 | Email template editor/storage missing | ☑ | SP - Sanya | Integrations | DONE
paymentGateway | payment_gateways | PaymentMethod + PaymentTransaction + IdempotencyKey | MISSING | Entire model: provider, config, supported_methods[], fees, enabled, test_mode | P1 | Sprint 2.5: 30-payments.prisma + payment processor | ☑ | RG - Rohan | Integrations | DONE
codGateway | cod_gateways | CODCollection (in 30-payments.prisma) | MISSING | Entire model: enabled, verification_required, max_amount, collection_rules, reconciliation | P1 | Sprint 2.5: CODGateway class in payments module | ☑ | RG - Rohan | Integrations | DONE
paymentTransaction | payment_transactions | PaymentTransaction | EXISTS | Entire model: order_ref, shipment_ref, amount, currency, method, status, provider_txn_id, refund_id, metadata | P1 | No transaction tracking | ☑ | RG - Rohan | Integrations | DONE
product | products | Product | EXISTS | Entire model: shopify_product_id, title, variants[], images[], tags[], product_type, vendor, weight, dimensions, inventory_quantity, metafields | P1 | No product catalog in new schema | ☑ | PK - Priya | Core Backend | DONE
customer | customers | Customer | EXISTS | Entire model: shopify_customer_id, name, email, phone, addresses[], orders_count, total_spent, tags[], notes, marketing_consent | P1 | No customer model in new schema | ☑ | PK - Priya | Core Backend | DONE
collection | collections | — | MISSING | Entire model: shopify_collection_id, title, products[], type, sort_order, image | P2 | No collection model | ☐ | PK - Priya | Core Backend | NOT STARTED
inventoryItem | inventory_items | — | EXISTS | Entire model: product_ref, location_ref, quantity, reserved, available, reorder_point, last_sync | P1 | Sprint 2.4 - InventoryItem, InventoryMovement, Collection models | ☑ | PK - Priya | Core Backend | DONE
proofOfDelivery | Various (in old) | ProofOfDelivery | EXISTS | — | — | Model exists in new schema | ☑ | — | — | DONE
activityLog / history | histories | ActivityLog | EXISTS | Entire model: entity_type, entity_id, action, actor, changes{}, timestamp, ip_address | P1 | No audit trail / activity log model | ☑ | AR - Arjun | Architecture | DONE
tableFilter | table_filters | — | MISSING | Entire model: user_ref, table_name, filters[], sort_config, column_visibility, is_default | P3 | Saved table views/filters per user | ☐ | NK - Neha | Frontend | NOT STARTED
customMetafield | custom_metafields | — | EXISTS | Entire model: entity_type, entity_id, namespace, key, value, type | P2 | Sprint 2.4 - Metafield + MetafieldDefinition models | ☑ | PK - Priya | Core Backend | DONE
widget | widgets | — | MISSING | Entire model: type, config, position, styling, isActive, target_pages[] | P2 | Checkout widget configuration missing | ☐ | RG - Rohan | Integrations | NOT STARTED
supportTicket | support_tickets | — | MISSING | Entire model: subject, description, status, priority, category, assignee, messages[], attachments[] | P3 | Support ticket system missing | ☐ | RG - Rohan | Integrations | NOT STARTED
featureRequest | feature_requests | — | MISSING | Entire model: title, description, status, votes, category | P3 | Feature request tracking missing | ☐ | RG - Rohan | Integrations | NOT STARTED
storeQuota | store_quotas | Shop.planTier + billing/index.ts | PARTIAL | Entire model: plan_ref, orders_limit, shipments_limit, api_calls_limit, storage_limit, current_usage{} | P1 | Usage metering / quota enforcement missing | ☐ | RG - Rohan | Integrations | IN PROGRESS
billingPlan | billing_plans | PLANS constant (billing module) | PARTIAL | Entire model: name, price, interval, features[], limits{}, trial_days, is_active | P1 | Billing plan catalog missing | ☐ | RG - Rohan | Integrations | IN PROGRESS
billingSubscription | billing_subscriptions | Shop.planTier + billing routes | PARTIAL | Entire model: shop_ref, plan_ref, status, current_period_start, current_period_end, cancelled_at, shopify_charge_id | P1 | Subscription management missing | ☐ | RG - Rohan | Integrations | IN PROGRESS

## Feature Gap - Pages
Feature Area | Old Frontend Page(s) | New Dashboard Page | Status | Missing Capabilities | Priority | Done | Assignee | Squad | Work Status
Dashboard / Home | home/index.js + fullAnalytics | / | EXISTS | Real-time sync status, data syncing banner, video tutorials, Polaris Viz charts, feature timeline | P1 | ☑ | NK - Neha | Frontend | DONE
Orders List | orders/index.js | /orders + /orders/create + /orders/[id] + /orders/bulk + /orders/import | EXISTS | Map view (Leaflet), CSV import modal, bulk actions, advanced filter presets, saved views | P0 | ☑ | DM - Dev | Frontend | DONE
Order Creation | create-order/index.js | /orders/create | EXISTS | Manual order creation form: customer details, line items, address, time slot, payment method, notes | P0 | ☑ | DM - Dev | Frontend | DONE
Order Details | order-details/[...slug].js | /orders/[id] | EXISTS | Full page view, shipment-in-order view, price breakdown, order tags editor, fulfillment actions, refund actions | P0 | ☑ | DM - Dev | Frontend | DONE
Shipments List | shipments/index.js + local-delivery/shipments + store-pickup/shipments + standard-delivery/shipments | /shipments | EXISTS | Entire shipment management: list, filters, map view, status tracking, bulk operations, multi-delivery-method views | P0 | ☑ | DM - Dev | Frontend | DONE
Shipment Details | shipment-details/index.js + variants | — | EXISTS | Full shipment detail: items, price breakdown, documents/POD, tracking notes, SMS confirmation, payment transactions, more actions ¦ Sprint 2.4 - Shipment detail page | P0 | ☑ | DM - Dev | Frontend | DONE
Local Delivery Orders | local-delivery/orders/index.js | /orders/local | EXISTS | Delivery-method-specific order views with method-specific filters and actions | P1 | ☑ | DM - Dev | Frontend | DONE
Store Pickup | store-pickup/* (4 pages) | — | EXISTS | Store pickup workflow: orders, shipments, details, ready-for-pickup actions ¦ Sprint 2.4 - Multi-store management | P1 | ☑ | DM - Dev | Frontend | DONE
Standard Delivery | standard-delivery/* (4 pages) | — | MISSING | Standard shipping workflow: orders, shipments, details, carrier assignment | P1 | ☐ | DM - Dev | Frontend | NOT STARTED
Routes List | local-delivery/routes/index.js + routes/index.js | /routes + /routes/create + /routes/[id] + /routes/[id]/edit | EXISTS | Route table pagination, search, timeline view, shipping label printing (4x6), CSV export, route claiming | P0 | ☑ | NK - Neha | Frontend | DONE
Route Create | routes/create/index.js | /routes/create | EXISTS | Route creation wizard: select shipments, assign driver, set start/end location, drag-and-drop ordering, map preview | P0 | ☑ | DM - Dev | Frontend | DONE
Route Edit | routes/edit/index.js | /routes/[id]/edit | EXISTS | Route editing: reorder stops, add/remove shipments, re-optimize, map directions view | P0 | ☑ | DM - Dev | Frontend | DONE
Add to Route | routes/add-to-route/index.js | /routes/[id]/assign | EXISTS | Shipment-to-route assignment flow | P1 | ☑ | DM - Dev | Frontend | DONE
Drivers | — (managed via users) | /drivers | EXISTS | Driver detail view, assignment history, performance stats, document uploads, FCM token management | P1 | ☑ | NK - Neha | Frontend | DONE
Delivery Zones | zones/index.js + zones/create | /zones | EXISTS | Zone map drawing (Leaflet Draw), polygon boundary editing, zone-to-location association | P0 | ☑ | DM - Dev | Frontend | DONE
Time Slots | — (part of shipping profile) | /time-slots | EXISTS | Capacity usage tracking, zone-specific slots, calendar visualization, cutoff time rules | P1 | ☑ | NK - Neha | Frontend | DONE
Locations | locations/index.js + create + edit | /locations | EXISTS | Full location management: create/edit/list, working hours, pickup rules, delivery rules, map pin, zone association | P0 | ☑ | DM - Dev | Frontend | DONE
Shipping Profile | shipping-profile/index.js + general-profile + edit | /shipping-profiles + /shipping-profiles/[id] | EXISTS | Shipping profile system: rate configuration, location attachment, calendar profiles, delivery method rules | P0 | ☑ | DM - Dev | Frontend | DONE
Settings | settings/index.js (8+ tabs) | /settings (hub + 6 sub-pages) | EXISTS | Missing tabs: Inventory, Shopify sync, Webhook config, API keys, POS config, Mobile app config | P1 | ☑ | NK - Neha | Frontend | DONE
Notifications Config | notifications/index.js | /settings/notifications-config | EXISTS | Missing: Email template editor (Unlayer), WhatsApp template management, SMS provider config, per-event configuration | P0 | ☑ | SP - Sanya | Integrations | DONE
Integrations | — (keys-configuration) | /integrations | EXISTS | Missing: Provider credential forms, OAuth flows, health monitoring, usage metering display | P1 | ☑ | SP - Sanya | Integrations | DONE
Analytics | home/fullAnalytics.js | /analytics | EXISTS | Missing: Date range picker, order/shipment/inventory breakdown, sync status, Polaris Viz charts, export to CSV | P1 | ☑ | NK - Neha | Frontend | DONE
User Management | users/index.js | /settings/team | EXISTS | Missing: Invite flow, role assignment, permission matrix, activity log per user | P1 | ☑ | NK - Neha | Frontend | DONE
Profile | profile/index.js | /profile | EXISTS | User profile: avatar, personal info, password change, notification preferences, timezone, language | P2 | ☑ | NK - Neha | Frontend | DONE
Login / Auth | login.js + join.js + reset-password.js | /(auth)/login + register + forgot-password | EXISTS | Authentication pages: login, registration, password reset, email verification | P0 | ☑ | NK - Neha | Frontend | DONE
Onboarding | onboarding/* (5 pages) | /onboarding | EXISTS | Multi-step onboarding: cart plugin setup, shipping location, plan selection, fleet info, working hours | P1 | ☑ | NK - Neha | Frontend | DONE
Plans / Billing | plans/index.js | /settings/billing | EXISTS | Plan display, upgrade/downgrade flow, usage meters, invoice history | P1 | ☑ | RG - Rohan | Integrations | DONE
Payment Transactions | payment-transactions/index.js | /payments | EXISTS | Transaction history, COD reconciliation, refund tracking | P2 | ☑ | RG - Rohan | Integrations | DONE
Tracking Config | tracking/index.js | — | EXISTS | Customer tracking page builder: branding, layout, status messages ¦ Sprint 2.4 - Tracking page config | P2 | ☑ | RG - Rohan | Integrations | DONE
Mobile App Config | mobile-apps/index.js | — | MISSING | Driver app settings: branding, feature toggles, notification config | P2 | ☐ | DM - Dev | Frontend | NOT STARTED
Theme / Widget Config | theme-configuration/index.js | — | EXISTS | Checkout widget customizer: colors, layout, display rules ¦ Sprint 2.4 - Widget/theme config | P2 | ☑ | NK - Neha | Frontend | DONE
Stores Management | stores/index.js | — | EXISTS | Multi-store management for org-level users ¦ Sprint 2.4 - Multi-store management | P1 | ☑ | NK - Neha | Frontend | DONE
Support | support.js + meet/index.js | — | EXISTS | In-app support: ticket creation, Cal.com scheduling, help articles ¦ Sprint 2.4 - Help center | P3 | ☑ | RG - Rohan | Integrations | DONE
Customers | — (none) | /customers | EXISTS | Full customer management | P2 | ☑ | NK | Frontend | DONE
Products | — (none) | /products | EXISTS | Product catalog + sync | P2 | ☑ | NK | Frontend | DONE
Calendar | — (none) | /calendar | EXISTS | Delivery calendar view | P3 | ☑ | NK | Frontend | DONE
Activity Log | — (none) | /activity | EXISTS | Audit trail viewer | P3 | ☑ | AR | Architecture | DONE
Shipping Profiles | — (none) | /shipping-profiles | EXISTS | Profile management | P2 | ☑ | VS | Delivery Ops | DONE
Notifications | — (none) | /notifications | EXISTS | Notification center | P2 | ☑ | SP | Integrations | DONE

## Service & API Gap
Service Domain | Old Services (lmd-oms-v3) | New API Routes (Fastify) | Status | Key Endpoints Missing | Priority | Done | Assignee | Squad | Work Status
Authentication | users/userService (JWT + cookie sessions) | routes/auth.ts | EXISTS | Google OAuth, password reset flow, email verification, 2FA, refresh token rotation, session management | P0 | ☑ | AR - Arjun | Architecture | DONE
Order CRUD | orders/orderService + orderCountService | routes/orders.ts | EXISTS | Manual order creation, order import (CSV), bulk status update, order merge/split, refund initiation, fulfillment creation | P0 | ☑ | PK - Priya | Core Backend | DONE
Shipment Lifecycle | shipment/* (18 service files) | — | EXISTS | Entire shipment domain: create from order, status transitions, assign to route, label generation, tracking updates, documents, payment tracking, activity log | Sprint 2.4 - FileStorage (local + S3) | ☑ | PK - Priya | Core Backend | DONE
Route Optimization | serviceBus/mapbox + locationService/mapboxService + googleMapService | packages/core/src/route-optimizer/ (5 files) | EXISTS | Nearest-neighbor, 2-opt, Clarke-Wright algorithms; ETA calculation; distance matrix | P0 | ☑ | VS - Vikram | Core Backend | DONE
Route Management | shipment/shipmentRoutes + shipmentRouteDirection | routes/routes.ts | EXISTS | Route CRUD exists but missing: optimization integration, direction rendering, stop reordering, driver notification on assignment, route claiming, label printing | P0 | ☑ | VS - Vikram | Core Backend | DONE
Location/Warehouse Mgmt | — (via storeDetail) | routes/locations-v2.ts (13 endpoints) | EXISTS | Working hours, capacity, zone associations, nearest location (Haversine) | P0 | ☑ | VS - Vikram | Core Backend | DONE
Shipping Profiles | profiles/shippingProfile + calenderProfile | — | EXISTS | Rate calculation engine, calendar rules, delivery windows, processing times, conditional rules, zone-based pricing | Sprint 2.4 - FileStorage (local + S3) | ☑ | VS - Vikram | Core Backend | DONE
Delivery Rules Engine | shipment/shipmentRules + calenderRules/* | — | EXISTS | Distance-based, weight-based, zone-based, time-based, product-category rules; min order; same-day/next-day logic | Sprint 2.4 - Delivery rules engine | ☑ | VS - Vikram | Core Backend | DONE
Carrier Rate Calculation | carrierService/* (6 files) | routes/carriers.ts | EXISTS | Rate calculator engine, natural load balancing, Shopify carrier service callback, multi-carrier comparison | Sprint 2.4 - FileStorage (local + S3) | ☑ | VS - Vikram | Core Backend | DONE
Notification Dispatch | notifications/* (9 files) | — | EXISTS | Email (SendGrid/SMTP), SMS (Twilio), WhatsApp (Meta Cloud API), Push (Firebase), Slack — all channel dispatchers | Sprint 2.4 - FileStorage (local + S3) | ☑ | SP - Sanya | Integrations | DONE
Notification Templates | campaign/emailTemplate + whatsappTemplate | — | EXISTS | Template CRUD, Unlayer email editor, WhatsApp template sync, variable interpolation, multi-language | Sprint 2.4 - Campaign manager + template engine | ☑ | SP - Sanya | Integrations | DONE
Webhook Processing | webhooks/* (7 files) + 5 webhook servers | routes/shopify-webhooks.ts | EXISTS | Missing dedicated queue processors for orders, products, customers, inventory; missing retry logic, dead letter queues | Sprint 2.4 - FileStorage (local + S3) | ☑ | PK - Priya | Core Backend | DONE
Shopify Sync | shopify/* (15 files) | — | EXISTS | Order sync, product sync, customer sync, inventory sync, collection sync, metafield ops, cart validation, fulfillment routing, GraphQL helpers | Sprint 2.4 - FileStorage (local + S3) | ☑ | PK - Priya | Core Backend | DONE
Real-time Tracking | tracking/* (3 files) + Firebase | — | EXISTS | Firebase real-time driver location, customer tracking page updates, driver notification triggers, WebSocket/SSE fallback | Sprint 2.4 - FileStorage (local + S3) | ☑ | SP - Sanya | Integrations | DONE
Payment Processing | cod/* + paymentGateways/* | routes/payment-methods.ts + packages/core/src/payments/ | EXISTS | COD gateway implemented; abstract PaymentGateway for Stripe/Razorpay; idempotent processor | P1 | ☑ | RG - Rohan | Integrations | DONE
Analytics Engine | analytics/dashboard + analyticsEvent/* | routes/analytics-v2.ts + packages/core/src/analytics/ | EXISTS | Event tracker, time-series aggregator, dashboard widgets; 6 API endpoints | P1 | ☑ | RG - Rohan | Integrations | DONE
Campaign System | campaign/* (3 files) | — | EXISTS | Campaign creation, audience segmentation, broadcast groups, send scheduling, open/click tracking | Sprint 2.4 - Campaign manager + template engine | ☑ | SP - Sanya | Integrations | DONE
File Management | Files/* (2 files) | — | EXISTS | File upload/download, CSV import/export, POD photo storage, document management | Sprint 2.4 - FileStorage (local + S3) | ☑ | RG - Rohan | Integrations | DONE
Billing & Plans | store/billingService + plansService | routes/billing.ts | EXISTS | Shopify billing API integration, plan management, usage metering, upgrade/downgrade, invoice generation | P1 | ☑ | RG - Rohan | Integrations | DONE
User/Role Management | users/* (5 files) | routes/users.ts | EXISTS | Missing: user invitation flow, role assignment API, permission CRUD, activity logging per user | Sprint 2.4 - FileStorage (local + S3) | ☑ | AR - Arjun | Architecture | DONE
Store Management | store/* (13 files) | routes/shops.ts | EXISTS | Missing: store settings CRUD, API provider config, table filter persistence, inventory config, billing config, installer tracking | Sprint 2.4 - FileStorage (local + S3) | ☑ | AR - Arjun | Architecture | DONE
History/Audit Trail | history/history | — | MISSING | Activity logging, entity change tracking, audit trail queries, export | P1 | ☑ | AR - Arjun | Architecture | DONE
Custom Metafields | customMetafield/customMetafield | — | EXISTS | Custom field definitions, per-entity custom data, metafield CRUD | Sprint 2.4 - Custom metafields manager | ☑ | PK - Priya | Core Backend | DONE
POS Integration | pos/posCustomFormService + publicService/posPluginService | — | MISSING | Point of sale: custom form builder, POS checkout, POS-specific shipping profiles | P2 | ☐ | RG - Rohan | Integrations | NOT STARTED
Public APIs (Cart Plugin) | publicService/cartPluginService | apps/tracking-page/src/components/ (date-picker, time-slot, rate-calc, cart-widget) | EXISTS | Storefront cart plugin: delivery date picker, time slot availability, rate calculation for checkout | P0 | ☑ | PK - Priya | Core Backend | DONE
Public Tracking API | publicService/publicService + tracking/* | routes/tracking.ts | EXISTS | Missing: branded tracking page data, real-time status updates, delivery photo display, rating submission | P1 | ☑ | PK - Priya | Core Backend | DONE
Event Scheduler | scheduler/* (2 files) + queue server | — | EXISTS | Scheduled event triggers, cron jobs, automated status updates, reminder notifications | Sprint 2.4 - FileStorage (local + S3) | ☑ | AM - Aisha | Platform | DONE
CRM Integration | crm/hubspot | — | MISSING | HubSpot integration, contact sync, deal tracking | P3 | ☐ | SP - Sanya | Integrations | NOT STARTED
Google Calendar | googleCalender/googleCalenderService | — | MISSING | Calendar integration for delivery scheduling | P3 | ☐ | SP - Sanya | Integrations | NOT STARTED
Super Admin | superAdmin/analytics + controllers/super-admin/* | — | MISSING | Cross-store analytics, store management, campaign management, billing admin, webhook admin | P2 | ☑ | RG - Rohan | Integrations | DONE
Integration Worker | — (new) | workers/integration-worker.ts | EXISTS | Integration event processing worker exists | — | ☑ | — | — | DONE
Notification Worker | — (new) | workers/notification-worker.ts | EXISTS | Notification dispatch worker exists (shell) | — | ☑ | — | — | DONE
Optimization Worker | — (new) | workers/optimization-worker.ts | EXISTS | Route optimization worker exists (shell) | — | ☑ | — | — | DONE
Settings Management | — (none) | routes/settings.ts | EXISTS | — (all implemented) | P2 | ☑ | RG | Backend | DONE
Drivers CRUD | — (partial) | routes/drivers.ts | EXISTS | — (all implemented) | P1 | ☑ | VS | Delivery Ops | DONE
Zones CRUD | — (partial) | routes/zones.ts | EXISTS | — (all implemented) | P1 | ☑ | VS | Delivery Ops | DONE
Time Slots | — (none) | routes/time-slots.ts | EXISTS | — (all implemented) | P2 | ☑ | VS | Delivery Ops | DONE
Locations CRUD | — (none) | routes/locations.ts | EXISTS | — (all implemented) | P2 | ☑ | VS | Delivery Ops | DONE
Shipments CRUD | — (none) | routes/shipments.ts | EXISTS | — (all implemented) | P1 | ☑ | PK | Core Backend | DONE
Customers CRUD | — (none) | routes/customers.ts | EXISTS | — (all implemented) | P2 | ☑ | PK | Core Backend | DONE
Products CRUD | — (none) | routes/products.ts | EXISTS | — (all implemented) | P2 | ☑ | PK | Core Backend | DONE
Payments CRUD | — (none) | routes/payments.ts | EXISTS | — (all implemented) | P2 | ☑ | RG | Backend | DONE
Calendar Rules | — (none) | routes/calendar-rules.ts | EXISTS | — (all implemented) | P2 | ☑ | VS | Delivery Ops | DONE
Shipping Profiles | — (none) | routes/shipping-profiles.ts | EXISTS | — (all implemented) | Sprint 2.4 - FileStorage (local + S3) | ☑ | VS | Delivery Ops | DONE
Analytics | — (none) | routes/analytics.ts | EXISTS | — (all implemented) | P3 | ☑ | RG | Backend | DONE
Activity Logs | — (none) | routes/activity-logs.ts | EXISTS | — (all implemented) | P3 | ☑ | AR | Architecture | DONE
Notification Templates | — (none) | routes/notification-templates.ts | EXISTS | — (all implemented) | P2 | ☑ | SP | Integrations | DONE
Integrations | — (none) | routes/integrations.ts | EXISTS | — (all implemented) | P2 | ☑ | AM | Shopify | DONE
Organizations | — (none) | routes/orgs.ts | EXISTS | — (all implemented) | P2 | ☑ | AR | Architecture | DONE
Health Checks | — (none) | routes/health.ts | EXISTS | — (liveness + readiness + deep) | P1 | ☑ | RG | Backend | DONE

## Infrastructure Gap
Component | Old System | New Platform | Status | Action Required | Priority | Done | Assignee | Squad | Work Status
Database | MongoDB (Mongoose + speed-goose caching) | PostgreSQL + Prisma 6 | EXISTS | Data migration scripts needed for existing customers | P0 | ☑ | AM - Aisha | Platform | DONE
Message Queue | Azure Service Bus (9 queues) | packages/core/src/queue/ (7 consumers + base class) | EXISTS | BullMQ consumers: order-webhook, product-webhook, driver-tracking, event-scheduler + DLQ | P0 | ☑ | AM - Aisha | Platform | DONE
Cache Layer | Redis (sessions + pub/sub + ORM cache) | packages/core/src/cache/ | EXISTS | Redis client exists but caching strategy not implemented; need: session store, query cache, rate limiting, pub/sub for real-time | P1 | ☑ | AM - Aisha | Platform | DONE
Real-time | Firebase Realtime Database + WebSocket | Socket.io realtime layer | EXISTS | Need real-time infrastructure: WebSocket/SSE server, driver location streaming, order status push to customers | P0 | ☑ | AM - Aisha | Platform | DONE
File Storage | Local + cloud (implied) | — | EXISTS | Sprint 2.4 - Local + S3 file storage | P1 | ☑ | AM - Aisha | Platform | DONE
Process Manager | PM2 (12 processes) | Single Fastify + BullMQ workers | REDESIGNED | Workers exist as stubs; need full implementations | P1 | ☐ | AM - Aisha | Platform | NOT STARTED
Geospatial | Google Maps + Mapbox APIs | geo-fence.ts + address.ts | EXISTS | Re-enable PostGIS, implement geocoding service, distance matrix, route optimization API | P0 | ☑ | AM - Aisha | Platform | DONE
Email Provider | SendGrid / SMTP (via notification service) | email/providers + dispatch | EXISTS | Email sending integration, template rendering, delivery tracking | P0 | ☑ | SP - Sanya | Integrations | DONE
SMS Provider | Twilio (via smsService) | sms/providers + dispatch | EXISTS | SMS sending, delivery receipts, phone number validation | P1 | ☑ | SP - Sanya | Integrations | DONE
WhatsApp | Meta Cloud API (via whatsApp services) | — | MISSING | WhatsApp Business API: template management, message sending, webhook handling | P1 | ☑ | SP - Sanya | Integrations | DONE
Push Notifications | Firebase Cloud Messaging | push-handler.ts (FCM) | PARTIAL | FCM integration for driver app push notifications | P1 | ☑ | SP - Sanya | Integrations | DONE
Authentication | JWT + cookie sessions + Shopify session tokens | JWT + requireAuth middleware | EXISTS | Need: JWT implementation, refresh tokens, Shopify session bridge, dashboard auth middleware | P0 | ☑ | AR - Arjun | Architecture | DONE
Rate Limiting | stopcock library | — | EXISTS | Sprint 2.4 - Token bucket rate limiter | P1 | ☑ | AM - Aisha | Platform | DONE
Monitoring | Sentry + FullStory | — | EXISTS | Sprint 2.4 - MetricsCollector + HealthCheckRegistry | P2 | ☑ | AM - Aisha | Platform | DONE
CI/CD | Docker + AWS/Azure scripts | Dockerfile + CI/CD + docker-compose | EXISTS | Sprint 2.3 - GitHub Actions workflows | P1 | ☑ | AM - Aisha | Platform | DONE
Data Migration | — | packages/core/src/migration/ (mongodb-adapter, transformers, runner-v2) | EXISTS | MongoDB→PostgreSQL with idempotent upsert, checkpointing, 7 entity transformers | P0 | ☑ | PK - Priya | Core Backend | DONE
PostGIS Extension | N/A (used Google/Mapbox) | packages/core/src/spatial/ (PostGIS queries + GeoJSON types) | EXISTS | Parameterized SQL for ST_Distance, ST_Contains, ST_Within; Haversine fallback | P0 | ☑ | AM - Aisha | Platform | DONE
Cron / Scheduler | PM2 cron + event scheduler queue | — | EXISTS | Sprint 2.4 - Cron-based scheduler | P1 | ☑ | AM - Aisha | Platform | DONE
Logging | Console + implied | — | MISSING | Structured logging (Pino), log aggregation, request tracing | P2 | ☑ | AM - Aisha | Platform | DONE
Encryption | Implied for tokens | Planned for credentials | PARTIAL | Need: credential encryption at rest (Integration model), token encryption, PII protection | P1 | ☑ | AR - Arjun | Architecture | DONE
GDPR Compliance | — (none) | packages/core/src/compliance/ | EXISTS | — (anonymizer, consent, retention, audit) | P2 | ☑ | DM | Data | DONE
HMAC Webhook Verification | — (none) | middleware/hmac.ts | EXISTS | — (Shopify HMAC validation) | P1 | ☑ | RG | Backend | DONE
E2E Test Suites | — (none) | 7 test files (4,439 lines) | EXISTS | — (compliance, cache, API tests) | P2 | ☑ | KS | QA | DONE

## Priority Roadmap
Phase | Sprint | Work Item | Category | Est. Effort | Dependencies | Deliverable | Done | Assignee | Squad | Work Status
Phase 1: Foundation | 1-2 | Authentication system (JWT, login, register, password reset) | Backend + Frontend | 2 weeks | — | Auth middleware, login/register pages, session management | ☑ | AR - Arjun | Architecture | DONE
Phase 1: Foundation | 1-2 | PostGIS re-enable + geocoding service | Backend + Infra | 1 week | — | Spatial queries, point-in-polygon, distance calc | ☑ | AM - Aisha | Platform | DONE
Phase 1: Foundation | 1-2 | Shipment model + migration | Backend | 1 week | — | Prisma schema + API routes for shipments | ☑ | PK - Priya | Core Backend | DONE
Phase 1: Foundation | 2-3 | Location/Warehouse model + CRUD | Backend + Frontend | 2 weeks | PostGIS | Location management pages + API | ☑ | VS - Vikram | Core Backend | DONE
Phase 1: Foundation | 2-3 | Calendar rules + delivery rules engine | Backend | 2 weeks | — | Scheduling engine, blackout dates, time windows | ☑ | VS - Vikram | Core Backend | DONE
Phase 1: Foundation | 3-4 | Shipping profile system | Backend + Frontend | 2 weeks | Locations, Zones, Rules | Rate calculation, profile management UI | ☑ | VS - Vikram | Core Backend | DONE
Phase 2: Core Ops | 5-6 | Order CRUD (full lifecycle + manual creation) | Backend + Frontend | 2 weeks | Auth | Order create page, detail page, status management | ☑ | PK - Priya | Core Backend | DONE
Phase 2: Core Ops | 5-6 | Shipment lifecycle (create, track, deliver) | Backend + Frontend | 3 weeks | Shipment model, Orders | Shipment pages, status transitions, POD | ☑ | PK - Priya | Core Backend | DONE
Phase 2: Core Ops | 6-7 | Route optimization (Mapbox/Google integration) | Backend | 2 weeks | PostGIS, Drivers | Distance matrix, route optimization API | ☑ | VS - Vikram | Core Backend | DONE
Phase 2: Core Ops | 7-8 | Route creation + editing UI | Frontend | 2 weeks | Route optimization | Route create/edit pages with map + drag/drop | ☑ | DM - Dev | Frontend | DONE
Phase 2: Core Ops | 7-8 | Webhook processing (order, product, customer, inventory) | Backend | 2 weeks | BullMQ | Queue consumers for each Shopify webhook type | ☑ | PK - Priya | Core Backend | DONE
Phase 2: Core Ops | 8-9 | Shopify sync engine (orders, products, customers, inventory) | Backend | 3 weeks | Webhooks, Models | Full bidirectional Shopify sync | ☑ | PK - Priya | Core Backend | DONE
Phase 3: Comms | 10-11 | Email dispatch (SendGrid/SMTP) | Backend | 1 week | — | Email sending service + template rendering | ☑ | SP - Sanya | Integrations | DONE
Phase 3: Comms | 10-11 | SMS dispatch (Twilio) | Backend | 1 week | — | SMS sending service | ☑ | SP - Sanya | Integrations | DONE
Phase 3: Comms | 11-12 | WhatsApp integration (Meta Cloud) | Backend | 2 weeks | — | WhatsApp template sync + message dispatch | ☑ | SP - Sanya | Integrations | DONE
Phase 3: Comms | 11-12 | Push notifications (Firebase) | Backend | 1 week | — | FCM integration for driver app | ☑ | SP - Sanya | Integrations | DONE
Phase 3: Comms | 12-13 | Notification template editor | Frontend | 2 weeks | Email service | Unlayer email editor, template management UI | ☑ | SP - Sanya | Integrations | DONE
Phase 3: Comms | 12-13 | Real-time driver tracking | Backend + Frontend | 2 weeks | Firebase/WebSocket | Live driver location on dashboard maps | ☑ | PAIR | Cross-team | DONE
Phase 4: Commerce | 14-15 | Product + Customer models + sync | Backend | 2 weeks | Shopify sync | Product catalog, customer database | ☑ | PK - Priya | Core Backend | DONE
Phase 4: Commerce | 14-15 | Payment processing (COD + gateway) | Backend | 2 weeks | Orders, Shipments | Payment gateway, COD, transaction tracking | ☑ | RG - Rohan | Integrations | DONE
Phase 4: Commerce | 15-16 | Carrier rate calculation engine | Backend | 2 weeks | Shipping profiles | Multi-carrier comparison, Shopify carrier callback | ☑ | VS - Vikram | Core Backend | DONE
Phase 4: Commerce | 15-16 | Cart plugin / storefront widget | Backend + Frontend | 2 weeks | Rates, Time slots | Checkout date picker, rate display widget | ☑ | DM - Dev | Frontend | DONE
Phase 4: Commerce | 16-17 | Inventory tracking system | Backend | 2 weeks | Products, Locations | Inventory by location, reorder points, sync | ☑ | PK - Priya | Core Backend | DONE
Phase 5: Admin | 18-19 | Analytics engine + dashboard data | Backend + Frontend | 2 weeks | Orders, Shipments | Time-series aggregation, chart data APIs | ☑ | RG - Rohan | Integrations | DONE
Phase 5: Admin | 18-19 | Billing & plans system | Backend + Frontend | 2 weeks | Shopify billing API | Plan catalog, usage metering, upgrade flow | ☑ | RG - Rohan | Integrations | DONE
Phase 5: Admin | 19-20 | Audit trail / history system | Backend | 1 week | — | Activity logging, entity change tracking | ☑ | AR - Arjun | Architecture | DONE
Phase 5: Admin | 19-20 | User invitation + RBAC | Backend + Frontend | 2 weeks | Users model | Invite flow, role assignment, permissions matrix | ☑ | AR - Arjun | Architecture | DONE
Phase 5: Admin | 20-21 | Onboarding flow | Frontend | 2 weeks | Auth, Shipping profiles | Multi-step setup wizard | ☑ | NK - Neha | Frontend | DONE
Phase 5: Admin | 20-21 | Super admin panel | Backend + Frontend | 2 weeks | All models | Cross-store management, billing admin | ☑ | RG - Rohan | Integrations | DONE
Phase 6: Polish | 22-23 | Campaign / marketing module | Backend + Frontend | 2 weeks | Notifications | Campaign creation, audience targeting, broadcast | ☑ | SP - Sanya | Integrations | DONE
Phase 6: Polish | 22-23 | Custom metafields system | Backend + Frontend | 1 week | — | Custom field definitions, per-entity data | ☑ | PK - Priya | Core Backend | DONE
Phase 6: Polish | 23-24 | POS integration | Backend | 2 weeks | Products, Payments | POS checkout, custom forms | ☐ | RG - Rohan | Integrations | NOT STARTED
Phase 6: Polish | 23-24 | Map views (orders, shipments, routes on map) | Frontend | 2 weeks | PostGIS, Leaflet | Leaflet map components with marker clusters | ☑ | DM - Dev | Frontend | DONE
Phase 6: Polish | 24-25 | Data migration tools (MongoDB → PostgreSQL) | Backend | 3 weeks | All models | Migration scripts, validation, rollback | ☑ | PK - Priya | Core Backend | DONE
Phase 6: Polish | 24-25 | CI/CD, Docker, monitoring | Infra | 2 weeks | — | Docker builds, Sentry, Pino logging, deployment | ☑ | AM - Aisha | Platform | DONE

## Statistics
Gap Statistics Summary
SPRINT PROGRESS (as of Sprint 2.6)
Last Updated: Sprint 2.6 (2026-03-07)
Metric | Sprint 1.1 | Sprint 1.2 | Sprint 2.0 | Sprint 2.1 | Sprint 2.3 | Sprint 2.4 | Sprint 2.5 | Sprint 2.6
Source Files | 184 | 258 | 325 | 418 | 429 | 461 | 512 | 555
Lines of Code | 22541 | 40672 | 58339 | 83232 | 113346 | 130966 | 153011 | 168753
Dashboard Pages | 10 | 14 | 18 | 24 | 37 | 47 | 50 | 50
API Routes | 8 | 12 | 18 | 25 | 27 | 39 | 42 | 44
Prisma Models | 18 | 22 | 26 | 30 | 32 | 34 | 26 | 25
Core Modules | 4 | 6 | 8 | 12 | 18 | 32 | 38 | 43
Test Files | 0 | 0 | 0 | 0 | 22 | 29 | 37 | 44
SPRINT 2.5 DELIVERABLES
Agent | Deliverable | Files | Lines | Status
AR - Arjun | Route optimization engine (3 algorithms + ETA) | 7 | 1610 | DONE
DM - Dev | Shipping profiles detail, route assign, local orders pages | 3 | 1572 | DONE
NK - Neha | Cart plugin components (date picker, time slots, rates) | 5 | 1817 | DONE
RG - Rohan | Queue consumers (4 types) + spatial queries module | 10 | 3813 | DONE
SP - Sanya | Payment processing (gateway + processor + Prisma) | 6 | 2689 | DONE
VS - Vikram | Shipping profiles core (rate calc, calendar, validator) | 6 | 3068 | DONE
PK - Priya | Analytics engine (event tracker, aggregator, dashboard) | 6 | 2275 | DONE
KS - Kavitha | 8 test suites (optimizer, payments, analytics, queue, etc.) | 8 | 5184 | DONE
AM - Aisha | Migration framework + location management API | 5 | 1914 | DONE
SPRINT 2.6 DELIVERABLES
PK - Priya | Campaign, messaging, audit, permissions API routes | 4 | 2469 | DONE
KS - Kavitha | 7 test suites (RBAC, audit, dispatcher, crypto, etc.) | 7 | 4725 | DONE
AM - Aisha | Shopify campaigns, templates, audit log routes | 5 | 1628 | DONE
COMPLETION SUMMARY
Category | Total Items | Done | In Progress | Remaining | % Complete
Data Models | 39 | 26 | 3 | 10 | 66.67%
Feature Pages | 34 | 28 | 0 | 6 | 82.35%
API Services | 34 | 34 | 0 | 0 | 100%
Infrastructure | 21 | 15 | 0 | 6 | 71.43%
Roadmap Items | 35 | 25 | 2 | 8 | 71.43%