## Team Directory
WITYLOGIX — STARTUP ENGINEERING TEAM
9-person team organized into 5 squads — working in parallel across 6 phases
ID | Name | Role | Squad | Focus Areas | Parallel Tracks | Models | Pages | Services | Infra | Roadmap | Total Items
AR | Arjun Rajput | CTO / Tech Lead | Architecture | System design, API architecture, DB schema, auth, infra decisions | Auth system, RBAC, schema design, code reviews
PK | Priya Kapoor | Sr. Backend Engineer | Core Backend | Order/shipment lifecycle, business logic, Shopify sync, webhooks | Order CRUD, shipment model, webhook processors, Shopify sync engine
VS | Vikram Shah | Backend Engineer | Core Backend | Route optimization, geospatial, carrier service, location mgmt | PostGIS, route optimization, shipping profiles, delivery rules, carrier rates
NK | Neha Krishnan | Sr. Frontend Engineer | Frontend | Dashboard UI, design system, pages, components, UX | Design system, dashboard pages, settings, analytics, onboarding
DM | Dev Malhotra | Frontend Engineer | Frontend | Order/shipment/route pages, map integrations, forms | Order pages, shipment pages, route create/edit, zone map drawing, forms
SP | Sanya Patel | Full-Stack Engineer | Integrations | Notification providers, email/SMS/WhatsApp, Firebase push, templates | SendGrid, Twilio, WhatsApp, FCM, notification templates, campaign system
RG | Rohan Gupta | Full-Stack Engineer | Integrations | Payment gateways, billing, analytics, 3rd-party APIs, super admin | Payment module, billing/plans, analytics engine, cart plugin, POS
AM | Aisha Mehra | DevOps / Infra Engineer | Platform | Docker, CI/CD, Redis, BullMQ, PostGIS, monitoring, deployment | Queue infrastructure, Redis caching, PostGIS setup, Docker, CI/CD, logging
KS | Kabir Singh | QA / Test Engineer | Quality | Test strategy, E2E tests, API tests, regression, data migration QA | Test framework setup, API test suites, E2E scenarios, migration validation
TOTAL
Squad Structure
Squad | Members | Primary Responsibility | Phase Focus
Architecture | AR (Arjun) | System design, auth, schema, cross-cutting concerns, code reviews | Phase 1 lead, oversight all phases
Core Backend | PK (Priya), VS (Vikram) | Order lifecycle, shipments, routes, shipping profiles, Shopify sync | Phase 1-2 primary, Phase 4 support
Frontend | NK (Neha), DM (Dev) | Dashboard UI, all pages, design system, map integrations, UX | Phase 1-2 primary (parallel with backend)
Integrations | SP (Sanya), RG (Rohan) | Notifications, payments, billing, analytics, 3rd-party APIs | Phase 3-4 primary, Phase 5-6
Platform | AM (Aisha) | Infrastructure, DevOps, queues, caching, monitoring, deployment | Phase 1 setup, continuous throughout
Quality | KS (Kabir) | Test strategy, automation, E2E, API tests, migration validation | Continuous from Phase 2 onwards

## Sprint 4.6 Plan (Done)
Agent | Role | Task | Files/Packages | Key Deliverables | Gap Ref | Status
AR - Arjun | CTO | Planned-vs-Actual Analytics Dashboard + ADR-025 | docs/adr/ADR-025-*.md, apps/dashboard/src/app/(dashboard)/analytics/* | Route analytics page, on-time %, driver scorecard, CO2 estimates, planned-vs-actual comparison, trend charts | G-10 | TODO
DM - Deepak | Frontend | Customer Portal v2 — Real-Time Tracking + Maps | apps/customer-portal/src/app/track/*, apps/customer-portal/src/components/live-map.tsx | Live WebSocket tracking, Leaflet map with driver position, ETA countdown, mobile-responsive polish, delivery history | — | TODO
NK - Nikhil | Frontend Lead | Google Maps Native UI Components | packages/ui/src/maps/*, apps/dashboard/src/components/maps/* | Address autocomplete, zone map visualization, embedded route map, draggable zone polygon editor, place search | G-09 | TODO
RG - Rahul | Backend Lead | WooCommerce REST API Adapter | packages/core/src/integrations/woocommerce/*, apps/api/src/routes/integrations/woocommerce.ts | Order sync (create/update/delete), product sync, customer sync, webhook consumer, WC REST v3 client, retry logic | G-08 | TODO
SP - Sanjay | Full-stack | Notification Preferences UI + WhatsApp Templates | apps/dashboard/src/app/(dashboard)/notifications/*, packages/core/src/notifications-v2/templates/* | Dashboard notification settings page, per-tenant channel config, WhatsApp template CRUD, delivery notification preview, test send | G-06 | TODO
VS - Vikram | Component Dev | Analytics Chart Components + KPI Library | apps/dashboard/src/components/analytics/*, apps/dashboard/src/components/ui/chart-*.tsx | Line chart, bar chart, pie chart, heatmap, KPI card, comparison card, sparkline, chart tooltip, responsive containers | — | TODO
PK - Priya | Sr. Backend | Invoice Engine Foundation | packages/core/src/invoicing/*, packages/db/prisma/schema/45-invoices.prisma, apps/api/src/routes/invoices.ts | Invoice model (8+ fields), per-delivery cost calc, PDF generation (pdfkit), invoice API (CRUD + send), Prisma schema | G-13 | TODO
KS - Kavitha | QA Lead | Integration Tests + Sprint 4.5 Unit Tests | tests/e2e/specs/integrations/*, tests/unit/woocommerce/*, tests/unit/analytics/* | WooCommerce adapter tests, analytics API tests, notification integration tests, POD unit tests, invoice API tests | — | TODO
AM - Aisha | Integration | WooCommerce Checkout Block + Platform Bridge | extensions/woocommerce-block/*, packages/core/src/integrations/woocommerce/checkout-block.ts | WC checkout block extension, delivery date picker for WC, Shopify-WC data normalizer, webhook normalization layer | G-08 | TODO
ZR - Zara | AI Engineer | Route Analytics ML — Efficiency & Prediction | packages/core/src/ai-analytics/*, apps/api/src/routes/ai/analytics.ts | Route efficiency scoring model, driver performance ML, delivery time prediction refinement, route anomaly detection, API endpoints | G-10 | TODO
THEME | Sprint 4.6 — Integrations, Analytics & Platform Maturity
GAP TARGETS | G-08 (WooCommerce), G-09 (Google Maps Native), G-10 (Planned-vs-Actual), G-13 (Invoice start)

## Executive Summary
WITYLOGIX PLATFORM — GAP ANALYSIS
Old Backend (lmd-oms-v3 + lmd-oms-nextjs-v3) → New Platform (witylogix-platform)
Last Updated: Sprint 3.0 (2026-03-08) | Old System | New Platform | Gap
Total Files: 555 source files ¦ 168,753 lines of code | 38+ | 26 (Prisma) | Consolidated into fewer, richer models
Sprints Completed: 1.1, 1.2, 2.0, 2.1, 2.2, 2.3, 2.4, 2.5 | 68 | 50 | Many features still need pages
API Routes | 85+ (Express) | 42 (Fastify) | Many endpoints still needed
Services/Controllers | 140+ / 80+ | 7+ queue consumers | Core business logic to rebuild
Microservices (PM2) | 12 | 1 monolith + workers | Queue workers needed
Notification Channels | Email, SMS, WhatsApp, Push, Slack | Schema only | All providers to integrate
Payment Systems | COD, Custom Gateways, Shopify Txn | COD + gateway abstractions | Stripe/Razorpay implementation needed
Map Providers | Google Maps + Mapbox | Haversine + PostGIS spatial module | PostGIS extension enable needed
Webhook Processors | 5 dedicated servers | 4 webhook consumers | Additional webhook types needed
Real-time Tracking | Firebase + WebSocket | None | Driver tracking to build
Campaign/Marketing | Email templates, Broadcasts | None | Campaign module needed
Integrations | 38 marketplace providers | Schema + registry | Provider implementations needed
Components | 296+ | ~12 | Component library to expand

## Competitive Gap Tracker
ID | Priority | Gap Item | Description | Effort | Competitive Leader | Sprint Target | Agent(s) | Status | Notes
G-01 | P0 | Customer Self-Service Portal | Build a full customer portal app (Next.js): order history with delivery status timeline, live GPS tracking on map, rescheduling flow (select new date/slot), delivery preferences (safe place instructions, preferred times, access codes), driver rating system, notification preference management. Currently ABSENT in all 6 competitors except Route4Me — massive first-mover opportunity for open-source. Reference: Route4Me has basic portal with order tracking + rescheduling. | L | Route4Me (only one) | 4.5 | DM | PLANNED | New app: apps/customer-portal/. React + Next.js. Auth via existing session manager.
G-02 | P0 | Checkout Date/Time Picker Widget | Build an embeddable checkout widget matching Pickeasy quality: date calendar with availability indicators, time slot grid showing remaining capacity per slot, zone-based delivery rate display, blackout date configuration, order cut-off/deadline engine (e.g. 'Friday pickup must be scheduled by Thursday 4pm'), zipcode/postcode validation with Google Maps, preparation time settings, product-specific delivery rules. Pickeasy has 8K+ merchants, 4.9 stars — this is the benchmark. ScrollEngine and Zapiet also strong here. | M | Pickeasy / ScrollEngine / Zapiet | 4.5 | NK, VS | PLANNED | Package: packages/checkout-widget/. Must be embeddable in Shopify, WooCommerce, standalone.
G-03 | P0 | POD Enhancement (Photo + Signature + QR + Timeline) | Upgrade proof-of-delivery to match Fleetbase + Routific: multi-method capture (photo of delivery at doorstep, e-signature pad, QR code scan, barcode verification), delivery status timeline UI (Planned → Out for Delivery → Delivered with timestamp + photo attachment), S3/R2 cloud storage for POD media, offline-capable POD capture that syncs when back online. Routific shows excellent UX with status timeline + photo proof. Fleetbase has QR + signature + manual methods. | M | Fleetbase + Routific | 4.5 | PK | PLANNED | packages/core/src/pod/. Driver app integration. Status timeline component for tracking page.
G-04 | P0 | Route Timeline Dispatcher Dashboard | Build Routific-quality dispatcher dashboard: interactive map showing color-coded routes per driver (10+ colors), timeline/Gantt view (8am-7pm) with stop dots per route, unscheduled vs scheduled orders toggle, real-time stats bar (active drivers, total stops, total km, estimated time), drag-and-drop route editing to reassign stops between drivers, 'Plan Routes' one-click optimization button. Reference: Routific screenshot shows 10 routes, 540 stops, 1200km, 65h 15m. | L | Routific | 4.5 | AR | PLANNED | apps/dashboard/src/app/(dashboard)/dispatch/. Uses Mapbox/Leaflet + D3 for timeline.
G-05 | P0 | Capacity Management & Zone Pricing | Implement Pickeasy/Zapiet-level slot capacity engine: daily order limits per slot, per-location capacity configuration, dynamic zone-based rate calculation (by zipcode, distance, weight, cart value, product type), multi-location support (20+ locations with separate configs), preparation time buffers between slots. Pickeasy and Zapiet both Strong here — essential for Shopify merchants. | S | Pickeasy / Zapiet | 4.5 | RG | PLANNED | packages/core/src/slots/. API endpoints: slot availability, rate calculator, capacity check.
G-06 | P1 | SMS/WhatsApp Customer Notifications | Build multi-channel notification engine: SMS via Twilio (delivery scheduled confirmation, out-for-delivery alert with tracking link + time window, delivered confirmation), WhatsApp via Meta Business API (rich media messages with map preview), email templates (branded HTML), push notifications (web + mobile). Routific pattern: 'Your delivery is scheduled between 3:00pm-5:00pm. Track here: [link]'. ScrollEngine leads on WhatsApp integration. | M | Routific / ScrollEngine | 4.5 | SP | PLANNED | packages/core/src/notifications-v2/. Template engine with variables. Webhook delivery status.
G-07 | P1 | Delivery Status Timeline UI | Visual delivery status timeline component: Planned (timestamp) → Out for Delivery (timestamp + driver name) → Delivered (timestamp + POD photo thumbnail). Used in customer portal, tracking page, and admin dashboard. Routific's implementation is the gold standard — clean vertical timeline with icons, timestamps, and photo attachment at final step. | S | Routific | 4.5 | VS, PK | PLANNED | Shared component in packages/checkout-widget/. Reused across portal, tracking page, dashboard.
G-08 | P1 | WooCommerce Deep Integration | Build WooCommerce REST API adapter: order sync (bidirectional), checkout widget embedding via WooCommerce blocks, shipping method integration, webhook handlers for order status changes, product sync for delivery rules. Route4Me has WooCommerce support — we need deeper integration to serve non-Shopify merchants. Currently our WooCommerce support is only 'Adequate'. | M | Route4Me | 4.6 | AM | PLANNED | packages/core/src/integrations/woocommerce/. REST API v3 adapter. Block-based widget.
G-09 | P1 | Google Maps & Calendar Integration | Native Google Maps integration for zone visualization (draw delivery zones on map, calculate distances), address autocomplete in checkout widget, driver route display on map. Google Calendar sync for merchant order reminders (auto-create calendar events for pickup orders). Pickeasy has both — merchants love the Calendar reminder feature. | S | Pickeasy | 4.6 | AM, NK | PLANNED | packages/core/src/integrations/google/. Maps JS API + Calendar API.
G-10 | P1 | Planned-vs-Actual Reporting | Route analytics dashboard: planned route vs actual GPS path overlay on map, on-time delivery percentage, average delivery time per zone, driver performance scorecard, CO2 emissions tracking per route (distance × vehicle type factor), weekly/monthly trend charts. Route4Me and Routific both have this — essential for fleet operations customers. | M | Route4Me / Routific | 4.6 | AR, ZR | PLANNED | apps/dashboard/src/app/(dashboard)/analytics/routes/. Chart.js + Mapbox.
G-11 | P2 | Telematics Gateway (Samsara + Geotab) | Build a telematics adapter layer supporting major providers: Samsara (real-time vehicle location, fuel level, engine diagnostics), Geotab (MyGeotab API for speed, idling, harsh braking), with plugin architecture for Verizon Connect, Motive, Azuga, Fleet Complete, NexTraq. Route4Me integrates all of these — it's the enterprise fleet differentiator. | L | Route4Me | 4.7 | AM, PK | PLANNED | packages/core/src/telematics/. Adapter pattern. Start with Samsara + Geotab SDKs.
G-12 | P2 | ML-Powered ETA Engine (Traffic-Aware) | Build traffic-aware ETA prediction: start with 3-5 ML models (time-of-day, day-of-week, historical delivery times, distance, traffic zone), integrate traffic data from Google Maps Directions API or TomTom, fallback to statistical model when ML unavailable. Long-term target: match Routific's 179 ML models. This directly improves customer experience and driver efficiency. | L | Routific (179 models) | 4.7 | ZR | PLANNED | packages/core/src/ai-eta/. TensorFlow.js or ONNX runtime. Model versioning.
G-13 | P2 | Automated Invoicing Engine | Build automated invoicing: generate invoices per delivery/route/customer with configurable billing rules (per-delivery, per-mile, per-hour, subscription), PDF invoice generation with company branding, email delivery, payment status tracking, QuickBooks/Xero integration adapter. Only Route4Me has this — enterprise fleet customers need automated billing. | M | Route4Me | 4.9 | RG, SP | PLANNED | packages/core/src/invoicing/. PDF generation. QuickBooks API adapter.
G-14 | P2 | Partner Directory & Courier Ecosystem | Build courier partner integration hub: adapters for Onfleet, Stuart, Uber Direct, Trexity, UniHop, Roadie (Zapiet's partner network), partner directory page in dashboard, API-based courier dispatch (auto-select cheapest/fastest courier), partner onboarding flow. Zapiet's partner ecosystem is a key competitive advantage — we need to match it. | M | Zapiet | 4.8 | AM, SP | PLANNED | packages/core/src/couriers/. Adapter per courier. Partner directory UI.
G-15 | P3 | AI Demand Prediction & Smart Scheduling | Build AI-powered demand prediction: forecast delivery volume by zone/day/hour using historical patterns, suggest optimal slot allocation, auto-adjust capacity limits based on predicted demand, driver availability forecasting. Nobody has this across all 6 competitors — it's a genuine first-mover opportunity that strengthens our AI positioning. | L | Nobody (first-mover) | 5.0+ | ZR | PLANNED | packages/core/src/ai-demand/. Time-series forecasting. Integration with slot engine.
SUMMARY | 15 competitive gaps: 5× P0 (Sprint 4.5), 5× P1 (Sprint 4.5-4.6), 4× P2 (Sprint 4.7-4.9), 1× P3 (Sprint 5.0+). Benchmarked against: Fleetbase, ScrollEngine, Zapiet, Route4Me, Routific, Pickeasy.

## Data Models Gap
Old Model (MongoDB) | Collection | New Model (Prisma) | Status | Key Fields Missing in New | Priority | Notes | Done | Assignee | Squad | Work Status
shopifyOrder | shopify_orders | Order | EXISTS | lineItems detail, billingAddress, shippingAddress, financialStatus, fulfillmentStatus, tags (rich), cancelledAt, refunds, discountCodes, taxLines, shippingLines, noteAttributes, orderRisk, orderSource | P0 | Core model - needs many Shopify-specific fields | ☑ | PK - Priya | Core Backend | DONE
shipment | shipments | Shipment | EXISTS | Entire model: tracking_number, carrier, shipping_method, status lifecycle, label_url, customs_info, insurance, return_tracking, package_dimensions, weight, estimated_delivery_date, actual_delivery_date, shipping_cost, recipient_details, documents[], activity_log[] | P0 | Critical gap - old system had full shipment lifecycle separate from orders | ☑ | PK - Priya | Core Backend | DONE
shipmentItem | shipment_items | ShipmentProof | EXISTS | Entire model: shipment_ref, product_id, variant_id, quantity, weight, dimensions, customs_value, hs_code, origin_country | P0 | Sprint 2.7 - 36-shipment-items.prisma | ☑ | PK - Priya | Core Backend | IN PROGRESS
user | users | User | EXISTS | phone, avatar, permissions[], timezone, language, lastActiveAt, inviteToken, inviteExpiry, twoFactorEnabled, notificationPreferences | P1 | Old had richer user profiles | ☑ | AR - Arjun | Architecture | DONE
userRole | user_roles | User.role (enum) | EXISTS | Full RBAC model with permissions array, resource-level access, customizable roles | P1 | Old had dynamic roles; new uses fixed enum | ☑ | AR - Arjun | Architecture | DONE
userPermission | user_permissions | — | MISSING | Entire model: role_ref, resource, action, allow/deny, conditions | P1 | Granular permission system missing | ☑ | AR - Arjun | Architecture | DONE
storeDetail | store_details | Shop | EXISTS | address, country, province, logo, favicon, social_links, business_hours, description, industry, defaultLanguage, supportEmail, returnPolicy, trackingPageConfig, widgetConfig, analyticsConfig | P1 | Shop model is minimal vs old storeDetail | ☑ | AR - Arjun | Architecture | DONE
storeSettings | store_settings | Shop.settings (JSON) | EXISTS | Structured settings: autoAssign, proofOfDelivery, signatureRequired, realTimeTracking, driverAppConfig, customerNotificationDefaults, inventorySync, fulfillmentRules | P1 | Old had explicit fields; new uses opaque JSON | ☑ | AR - Arjun | Architecture | DONE
storeApiSettings | store_api_settings | Integration | EXISTS | Old had dedicated model for API keys per provider (Google, Mapbox, Twilio, SendGrid, etc.) | P2 | Subsumed by Integration model but less explicit | ☑ | SP - Sanya | Integrations | DONE
storeInfo | store_infos | Shop | EXISTS | Merged into Shop model | — | Consolidated correctly | ☑ | — | — | DONE
calenderRule / calenderProfile | calender_rules / calender_profiles | — | MISSING | Entire models: blackout_dates[], operating_hours{}, preparation_time, cutoff_rules, holiday_calendars, recurring_rules, capacity_by_day, special_event_overrides | P0 | Sprint 2.5: calendar-engine.ts in shipping-profiles module | ☑ | VS - Vikram | Core Backend | DONE
deliveryRule / pickupRule / shippingRule | Various | — | EXISTS | Entire rule engines: distance-based, weight-based, zone-based, product-category, minimum-order, time-window, same-day/next-day rules, rate tables, conditional logic | P0 | Sprint 2.4 - DeliveryRule, PickupRule, CalendarProfile models added | ☑ | VS - Vikram | Core Backend | DONE
shippingProfile | shipping_profiles | ShippingProfile + ShippingRate + ShippingZoneRule + DeliveryCalendar | MISSING | Entire model: locations[], rates[], rules[], zones[], delivery_methods[], processing_times, conditions, product_groups | P0 | Sprint 2.5: 31-shipping-profiles-v2.prisma + full core module | ☑ | VS - Vikram | Core Backend | DONE
zone | zones | DeliveryZone | EXISTS | boundary polygon (PostGIS), color, description, delivery_methods[], associated_locations[], max_distance, estimated_time_range | P1 | PostGIS boundary is TODO; zone features limited | ☑ | VS - Vikram | Core Backend | DONE
location / warehouse | locations | Location | EXISTS | Entire model: name, address, coordinates, type (warehouse/store/hub), inventory[], working_hours, pickup_rules, delivery_rules, associated_zones[], capacity, contact_info | P0 | No location/warehouse model in new schema | ☑ | VS - Vikram | Core Backend | DONE
vehicle | vehicles | Driver (with vehicle fields) | EXISTS | Old had separate Vehicle model: make, model, year, color, insurance, registration, capacity_volume, capacity_weight, fuel_type, maintenance_schedule | P2 | New schema has vehicleType/vehiclePlate on Driver only | ☑ | VS - Vikram | Core Backend | DONE
notificationTemplate | notification_templates | NotificationTemplate | EXISTS | Entire model: channel, event_type, subject, body_template, variables[], isActive, language, version | P1 | Notification template system missing | ☑ | SP - Sanya | Integrations | DONE
notificationConfig | notification_configs | NotificationLog | EXISTS | Per-store notification preferences: enabled_channels{}, event_subscriptions{}, quiet_hours, frequency_limits | P1 | Notification configuration missing | ☑ | SP - Sanya | Integrations | DONE
whatsappTemplate | whatsapp_templates | — | MISSING | Entire model: template_id, name, language, category, components[], status, provider_template_id | P2 | WhatsApp Business template management | ☑ | SP - Sanya | Integrations | DONE
campaign | campaigns | — | MISSING | Entire model: name, type, audience_filter, template_ref, schedule, status, sent_count, open_rate, click_rate | P2 | Campaign/marketing module missing | ☑ | SP - Sanya | Integrations | DONE
broadcastGroup | broadcast_groups | — | MISSING | Entire model: name, type, member_filter, members[], metadata | P2 | Broadcast targeting missing | ☑ | SP - Sanya | Integrations | DONE
emailTemplate | email_templates | — | MISSING | Entire model: name, subject, html_body, design_json (Unlayer), category, variables[] | P2 | Email template editor/storage missing | ☑ | SP - Sanya | Integrations | DONE
paymentGateway | payment_gateways | PaymentMethod + PaymentTransaction + IdempotencyKey | MISSING | Entire model: provider, config, supported_methods[], fees, enabled, test_mode | P1 | Sprint 2.5: 30-payments.prisma + payment processor | ☑ | RG - Rohan | Integrations | DONE
codGateway | cod_gateways | CODCollection (in 30-payments.prisma) | MISSING | Entire model: enabled, verification_required, max_amount, collection_rules, reconciliation | P1 | Sprint 2.5: CODGateway class in payments module | ☑ | RG - Rohan | Integrations | DONE
paymentTransaction | payment_transactions | PaymentTransaction | EXISTS | Entire model: order_ref, shipment_ref, amount, currency, method, status, provider_txn_id, refund_id, metadata | P1 | No transaction tracking | ☑ | RG - Rohan | Integrations | DONE
product | products | Product | EXISTS | Entire model: shopify_product_id, title, variants[], images[], tags[], product_type, vendor, weight, dimensions, inventory_quantity, metafields | P1 | No product catalog in new schema | ☑ | PK - Priya | Core Backend | DONE
customer | customers | Customer | EXISTS | Entire model: shopify_customer_id, name, email, phone, addresses[], orders_count, total_spent, tags[], notes, marketing_consent | P1 | No customer model in new schema | ☑ | PK - Priya | Core Backend | DONE
collection | collections | — | EXISTS | Entire model: shopify_collection_id, title, products[], type, sort_order, image | P2 | Sprint 2.7 | ☑ | PK - Priya | Core Backend | NOT STARTED
inventoryItem | inventory_items | — | EXISTS | Entire model: product_ref, location_ref, quantity, reserved, available, reorder_point, last_sync | P1 | Sprint 2.4 - InventoryItem, InventoryMovement, Collection models | ☑ | PK - Priya | Core Backend | DONE
proofOfDelivery | Various (in old) | ProofOfDelivery | EXISTS | — | — | Model exists in new schema | ☑ | — | — | DONE
activityLog / history | histories | ActivityLog | EXISTS | Entire model: entity_type, entity_id, action, actor, changes{}, timestamp, ip_address | P1 | No audit trail / activity log model | ☑ | AR - Arjun | Architecture | DONE
tableFilter | table_filters | — | EXISTS | Entire model: user_ref, table_name, filters[], sort_config, column_visibility, is_default | P3 | Sprint 2.7 | ☑ | NK - Neha | Frontend | NOT STARTED
customMetafield | custom_metafields | — | EXISTS | Entire model: entity_type, entity_id, namespace, key, value, type | P2 | Sprint 2.4 - Metafield + MetafieldDefinition models | ☑ | PK - Priya | Core Backend | DONE
widget | widgets | — | EXISTS | Entire model: type, config, position, styling, isActive, target_pages[] | P2 | Sprint 2.7 | ☑ | RG - Rohan | Integrations | NOT STARTED
supportTicket | support_tickets | — | EXISTS | Entire model: subject, description, status, priority, category, assignee, messages[], attachments[] | P3 | Sprint 2.7 | ☑ | RG - Rohan | Integrations | NOT STARTED
featureRequest | feature_requests | — | EXISTS | Entire model: title, description, status, votes, category | P3 | Sprint 2.7 | ☑ | RG - Rohan | Integrations | NOT STARTED
storeQuota | store_quotas | Shop.planTier + billing/index.ts | EXISTS | Entire model: plan_ref, orders_limit, shipments_limit, api_calls_limit, storage_limit, current_usage{} | P1 | Sprint 2.7 | ☑ | RG - Rohan | Integrations | IN PROGRESS
billingPlan | billing_plans | PLANS constant (billing module) | EXISTS | Entire model: name, price, interval, features[], limits{}, trial_days, is_active | P1 | Sprint 2.7 | ☑ | RG - Rohan | Integrations | IN PROGRESS
billingSubscription | billing_subscriptions | Shop.planTier + billing routes | EXISTS | Entire model: shop_ref, plan_ref, status, current_period_start, current_period_end, cancelled_at, shopify_charge_id | P1 | Sprint 2.7 | ☑ | RG - Rohan | Integrations | IN PROGRESS
SPRINT 2.8 PLANNED
authProvider | auth_providers | AuthProvider | PLANNED | provider, type (auth0/clerk/cognito/firebase), config, enabled, tenant_scope | P1 | Sprint 2.8 - Auth provider registry | ☐
authSession | auth_sessions | AuthSession | PLANNED | userId, provider, externalId, accessToken, refreshToken, expiresAt, metadata | P1 | Sprint 2.8 - External auth sessions | ☐
platformAdmin | platform_admins | PlatformAdmin | PLANNED | email, role (super/admin/support), permissions, lastLogin, mfaEnabled | P1 | Sprint 2.8 - Platform admin panel | ☐
posConfig | pos_configs | POSConfig | PLANNED | shopId, formSchema, checkoutRules, shippingProfileRef | P2 | Sprint 2.8 - POS integration | ☐

## Feature Gap - Pages
Feature Area | Old Frontend Page(s) | New Dashboard Page | Status | Missing Capabilities | Priority | Done | Assignee | Squad | Work Status
Dashboard / Home | home/index.js + fullAnalytics | / | EXISTS | Real-time sync status, data syncing banner, video tutorials, Polaris Viz charts, feature timeline | P1 | ☑ | NK - Neha | Frontend | DONE
Orders List | orders/index.js | /orders + /orders/create + /orders/[id] + /orders/bulk + /orders/import | EXISTS | Map view (Leaflet), CSV import modal, bulk actions, advanced filter presets, saved views | P0 | ☑ | DM - Dev | Frontend | DONE
Order Creation | create-order/index.js | /orders/create | EXISTS | Manual order creation form: customer details, line items, address, time slot, payment method, notes | P0 | ☑ | DM - Dev | Frontend | DONE
Order Details | order-details/[...slug].js | /orders/[id] | EXISTS | Full page view, shipment-in-order view, price breakdown, order tags editor, fulfillment actions, refund actions | P0 | ☑ | DM - Dev | Frontend | DONE
Shipments List | shipments/index.js + local-delivery/shipments + store-pickup/shipments + standard-delivery/shipments | /shipments | EXISTS | Entire shipment management: list, filters, map view, status tracking, bulk operations, multi-delivery-method views | P0 | ☑ | DM - Dev | Frontend | DONE
Shipment Details | shipment-details/index.js + variants | — | EXISTS | Full shipment detail: items, price breakdown, documents/POD, tracking notes, SMS confirmation, payment transactions, more actions ¦ Sprint 2.4 - Shipment detail page | P0 | ☑ | DM - Dev | Frontend | DONE
Local Delivery Orders | local-delivery/orders/index.js | /orders/local | EXISTS | Delivery-method-specific order views with method-specific filters and actions | P1 | ☑ | DM - Dev | Frontend | DONE
Store Pickup | store-pickup/* (4 pages) | — | EXISTS | Store pickup workflow: orders, shipments, details, ready-for-pickup actions ¦ Sprint 2.4 - Multi-store management | P1 | ☑ | DM - Dev | Frontend | DONE
Standard Delivery | standard-delivery/* (4 pages) | — | MISSING | Standard shipping workflow: orders, shipments, details, carrier assignment | P1 | ☐ | DM - Dev | Frontend | NOT STARTED
Routes List | local-delivery/routes/index.js + routes/index.js | /routes + /routes/create + /routes/[id] + /routes/[id]/edit | EXISTS | Route table pagination, search, timeline view, shipping label printing (4x6), CSV export, route claiming | P0 | ☑ | NK - Neha | Frontend | DONE
Route Create | routes/create/index.js | /routes/create | EXISTS | Route creation wizard: select shipments, assign driver, set start/end location, drag-and-drop ordering, map preview | P0 | ☑ | DM - Dev | Frontend | DONE
Route Edit | routes/edit/index.js | /routes/[id]/edit | EXISTS | Route editing: reorder stops, add/remove shipments, re-optimize, map directions view | P0 | ☑ | DM - Dev | Frontend | DONE
Add to Route | routes/add-to-route/index.js | /routes/[id]/assign | EXISTS | Shipment-to-route assignment flow | P1 | ☑ | DM - Dev | Frontend | DONE
Drivers | — (managed via users) | /drivers | EXISTS | Driver detail view, assignment history, performance stats, document uploads, FCM token management | P1 | ☑ | NK - Neha | Frontend | DONE
Delivery Zones | zones/index.js + zones/create | /zones | EXISTS | Zone map drawing (Leaflet Draw), polygon boundary editing, zone-to-location association | P0 | ☑ | DM - Dev | Frontend | DONE
Time Slots | — (part of shipping profile) | /time-slots | EXISTS | Capacity usage tracking, zone-specific slots, calendar visualization, cutoff time rules | P1 | ☑ | NK - Neha | Frontend | DONE
Locations | locations/index.js + create + edit | /locations | EXISTS | Full location management: create/edit/list, working hours, pickup rules, delivery rules, map pin, zone association | P0 | ☑ | DM - Dev | Frontend | DONE
Shipping Profile | shipping-profile/index.js + general-profile + edit | /shipping-profiles + /shipping-profiles/[id] | EXISTS | Shipping profile system: rate configuration, location attachment, calendar profiles, delivery method rules | P0 | ☑ | DM - Dev | Frontend | DONE
Settings | settings/index.js (8+ tabs) | /settings (hub + 6 sub-pages) | EXISTS | Missing tabs: Inventory, Shopify sync, Webhook config, API keys, POS config, Mobile app config | P1 | ☑ | NK - Neha | Frontend | DONE
Notifications Config | notifications/index.js | /settings/notifications-config | EXISTS | Missing: Email template editor (Unlayer), WhatsApp template management, SMS provider config, per-event configuration | P0 | ☑ | SP - Sanya | Integrations | DONE
Integrations | — (keys-configuration) | /integrations | EXISTS | Missing: Provider credential forms, OAuth flows, health monitoring, usage metering display | P1 | ☑ | SP - Sanya | Integrations | DONE
Analytics | home/fullAnalytics.js | /analytics | EXISTS | Missing: Date range picker, order/shipment/inventory breakdown, sync status, Polaris Viz charts, export to CSV | P1 | ☑ | NK - Neha | Frontend | DONE
User Management | users/index.js | /settings/team | EXISTS | Missing: Invite flow, role assignment, permission matrix, activity log per user | P1 | ☑ | NK - Neha | Frontend | DONE
Profile | profile/index.js | /profile | EXISTS | User profile: avatar, personal info, password change, notification preferences, timezone, language | P2 | ☑ | NK - Neha | Frontend | DONE
Login / Auth | login.js + join.js + reset-password.js | /(auth)/login + register + forgot-password | EXISTS | Authentication pages: login, registration, password reset, email verification | P0 | ☑ | NK - Neha | Frontend | DONE
Onboarding | onboarding/* (5 pages) | /onboarding | EXISTS | Multi-step onboarding: cart plugin setup, shipping location, plan selection, fleet info, working hours | P1 | ☑ | NK - Neha | Frontend | DONE
Plans / Billing | plans/index.js | /settings/billing | EXISTS | Plan display, upgrade/downgrade flow, usage meters, invoice history | P1 | ☑ | RG - Rohan | Integrations | DONE
Payment Transactions | payment-transactions/index.js | /payments | EXISTS | Transaction history, COD reconciliation, refund tracking | P2 | ☑ | RG - Rohan | Integrations | DONE
Tracking Config | tracking/index.js | — | EXISTS | Customer tracking page builder: branding, layout, status messages ¦ Sprint 2.4 - Tracking page config | P2 | ☑ | RG - Rohan | Integrations | DONE
Mobile App Config | mobile-apps/index.js | — | EXISTS | Driver app settings: branding, feature toggles, notification config | Sprint 2.7 | ☑ | DM - Dev | Frontend | NOT STARTED
Theme / Widget Config | theme-configuration/index.js | — | EXISTS | Checkout widget customizer: colors, layout, display rules ¦ Sprint 2.4 - Widget/theme config | P2 | ☑ | NK - Neha | Frontend | DONE
Stores Management | stores/index.js | — | EXISTS | Multi-store management for org-level users ¦ Sprint 2.4 - Multi-store management | P1 | ☑ | NK - Neha | Frontend | DONE
Support | support.js + meet/index.js | — | EXISTS | In-app support: ticket creation, Cal.com scheduling, help articles ¦ Sprint 2.4 - Help center | P3 | ☑ | RG - Rohan | Integrations | DONE
Customers | — (none) | /customers | EXISTS | Full customer management | P2 | ☑ | NK | Frontend | DONE
Products | — (none) | /products | EXISTS | Product catalog + sync | P2 | ☑ | NK | Frontend | DONE
Calendar | — (none) | /calendar | EXISTS | Delivery calendar view | P3 | ☑ | NK | Frontend | DONE
Activity Log | — (none) | /activity | EXISTS | Audit trail viewer | P3 | ☑ | AR | Architecture | DONE
Shipping Profiles | — (none) | /shipping-profiles | EXISTS | Profile management | P2 | ☑ | VS | Delivery Ops | DONE
Notifications | — (none) | /notifications | EXISTS | Notification center | P2 | ☑ | SP | Integrations | DONE
SPRINT 2.8 PLANNED
Activity Log (Redesign) | activity log viewer | /activity | PLANNED | Full audit trail with filters, timeline, entity links, export — frontend-design skill | P1 | ☐ | DM - Dev
Settings Hub (Redesign) | settings/* (8+ tabs) | /settings/* | PLANNED | Unified settings with auth providers, branding, API keys, team — frontend-design skill | P1 | ☐ | NK - Neha
Platform Admin Panel | — (new) | /admin/* | PLANNED | User management, customer management, store oversight, metrics, platform config | P1 | ☐ | DM - Dev
Standard Delivery | standard-delivery/* | /delivery/standard | PLANNED | Standard shipping workflow: orders, shipments, carrier assignment | P1 | ☐ | NK - Neha
Auth Provider Config | — (new) | /settings/auth-providers | PLANNED | Auth0/Clerk/Cognito/Firebase provider setup, test connection, SAML/OIDC config | P1 | ☐ | NK - Neha
DESIGN SYSTEM (Sprint 3.0)
shadcn/ui Component Preview | Interactive component gallery with dark theme | Sprint 3.0 | Planned
Design Tokens Page | Visual token reference (colors, spacing, typography) | Sprint 3.0 | Planned
Webhook Management | Register, test, and monitor webhook endpoints | Sprint 3.0 | Planned
Event Log Viewer | Browse and filter platform event stream | Sprint 3.0 | Planned

## Service & API Gap
Service Domain | Old Services (lmd-oms-v3) | New API Routes (Fastify) | Status | Key Endpoints Missing | Priority | Done | Assignee | Squad | Work Status
Authentication | users/userService (JWT + cookie sessions) | routes/auth.ts | EXISTS | Google OAuth, password reset flow, email verification, 2FA, refresh token rotation, session management | P0 | ☑ | AR - Arjun | Architecture | DONE
Order CRUD | orders/orderService + orderCountService | routes/orders.ts | EXISTS | Manual order creation, order import (CSV), bulk status update, order merge/split, refund initiation, fulfillment creation | P0 | ☑ | PK - Priya | Core Backend | DONE
Shipment Lifecycle | shipment/* (18 service files) | — | EXISTS | Entire shipment domain: create from order, status transitions, assign to route, label generation, tracking updates, documents, payment tracking, activity log | Sprint 2.4 - FileStorage (local + S3) | ☑ | PK - Priya | Core Backend | DONE
Route Optimization | serviceBus/mapbox + locationService/mapboxService + googleMapService | packages/core/src/route-optimizer/ (5 files) | EXISTS | Nearest-neighbor, 2-opt, Clarke-Wright algorithms; ETA calculation; distance matrix | P0 | ☑ | VS - Vikram | Core Backend | DONE
Route Management | shipment/shipmentRoutes + shipmentRouteDirection | routes/routes.ts | EXISTS | Route CRUD exists but missing: optimization integration, direction rendering, stop reordering, driver notification on assignment, route claiming, label printing | P0 | ☑ | VS - Vikram | Core Backend | DONE
Location/Warehouse Mgmt | — (via storeDetail) | routes/locations-v2.ts (13 endpoints) | EXISTS | Working hours, capacity, zone associations, nearest location (Haversine) | P0 | ☑ | VS - Vikram | Core Backend | DONE
Shipping Profiles | profiles/shippingProfile + calenderProfile | — | EXISTS | Rate calculation engine, calendar rules, delivery windows, processing times, conditional rules, zone-based pricing | Sprint 2.4 - FileStorage (local + S3) | ☑ | VS - Vikram | Core Backend | DONE
Delivery Rules Engine | shipment/shipmentRules + calenderRules/* | — | EXISTS | Distance-based, weight-based, zone-based, time-based, product-category rules; min order; same-day/next-day logic | Sprint 2.4 - Delivery rules engine | ☑ | VS - Vikram | Core Backend | DONE
Carrier Rate Calculation | carrierService/* (6 files) | routes/carriers.ts | EXISTS | Rate calculator engine, natural load balancing, Shopify carrier service callback, multi-carrier comparison | Sprint 2.4 - FileStorage (local + S3) | ☑ | VS - Vikram | Core Backend | DONE
Notification Dispatch | notifications/* (9 files) | — | EXISTS | Email (SendGrid/SMTP), SMS (Twilio), WhatsApp (Meta Cloud API), Push (Firebase), Slack — all channel dispatchers | Sprint 2.4 - FileStorage (local + S3) | ☑ | SP - Sanya | Integrations | DONE
Notification Templates | campaign/emailTemplate + whatsappTemplate | — | EXISTS | Template CRUD, Unlayer email editor, WhatsApp template sync, variable interpolation, multi-language | Sprint 2.4 - Campaign manager + template engine | ☑ | SP - Sanya | Integrations | DONE
Webhook Processing | webhooks/* (7 files) + 5 webhook servers | routes/shopify-webhooks.ts | EXISTS | Missing dedicated queue processors for orders, products, customers, inventory; missing retry logic, dead letter queues | Sprint 2.4 - FileStorage (local + S3) | ☑ | PK - Priya | Core Backend | DONE
Shopify Sync | shopify/* (15 files) | — | EXISTS | Order sync, product sync, customer sync, inventory sync, collection sync, metafield ops, cart validation, fulfillment routing, GraphQL helpers | Sprint 2.4 - FileStorage (local + S3) | ☑ | PK - Priya | Core Backend | DONE
Real-time Tracking | tracking/* (3 files) + Firebase | — | EXISTS | Firebase real-time driver location, customer tracking page updates, driver notification triggers, WebSocket/SSE fallback | Sprint 2.4 - FileStorage (local + S3) | ☑ | SP - Sanya | Integrations | DONE
Payment Processing | cod/* + paymentGateways/* | routes/payment-methods.ts + packages/core/src/payments/ | EXISTS | COD gateway implemented; abstract PaymentGateway for Stripe/Razorpay; idempotent processor | P1 | ☑ | RG - Rohan | Integrations | DONE
Analytics Engine | analytics/dashboard + analyticsEvent/* | routes/analytics-v2.ts + packages/core/src/analytics/ | EXISTS | Event tracker, time-series aggregator, dashboard widgets; 6 API endpoints | P1 | ☑ | RG - Rohan | Integrations | DONE
Campaign System | campaign/* (3 files) | — | EXISTS | Campaign creation, audience segmentation, broadcast groups, send scheduling, open/click tracking | Sprint 2.4 - Campaign manager + template engine | ☑ | SP - Sanya | Integrations | DONE
File Management | Files/* (2 files) | — | EXISTS | File upload/download, CSV import/export, POD photo storage, document management | Sprint 2.4 - FileStorage (local + S3) | ☑ | RG - Rohan | Integrations | DONE
Billing & Plans | store/billingService + plansService | routes/billing.ts | EXISTS | Shopify billing API integration, plan management, usage metering, upgrade/downgrade, invoice generation | P1 | ☑ | RG - Rohan | Integrations | DONE
User/Role Management | users/* (5 files) | routes/users.ts | EXISTS | Missing: user invitation flow, role assignment API, permission CRUD, activity logging per user | Sprint 2.4 - FileStorage (local + S3) | ☑ | AR - Arjun | Architecture | DONE
Store Management | store/* (13 files) | routes/shops.ts | EXISTS | Missing: store settings CRUD, API provider config, table filter persistence, inventory config, billing config, installer tracking | Sprint 2.4 - FileStorage (local + S3) | ☑ | AR - Arjun | Architecture | DONE
History/Audit Trail | history/history | — | MISSING | Activity logging, entity change tracking, audit trail queries, export | P1 | ☑ | AR - Arjun | Architecture | DONE
Custom Metafields | customMetafield/customMetafield | — | EXISTS | Custom field definitions, per-entity custom data, metafield CRUD | Sprint 2.4 - Custom metafields manager | ☑ | PK - Priya | Core Backend | DONE
POS Integration | pos/posCustomFormService + publicService/posPluginService | — | MISSING | Point of sale: custom form builder, POS checkout, POS-specific shipping profiles | P2 | ☐ | RG - Rohan | Integrations | NOT STARTED
Public APIs (Cart Plugin) | publicService/cartPluginService | apps/tracking-page/src/components/ (date-picker, time-slot, rate-calc, cart-widget) | EXISTS | Storefront cart plugin: delivery date picker, time slot availability, rate calculation for checkout | P0 | ☑ | PK - Priya | Core Backend | DONE
Public Tracking API | publicService/publicService + tracking/* | routes/tracking.ts | EXISTS | Missing: branded tracking page data, real-time status updates, delivery photo display, rating submission | P1 | ☑ | PK - Priya | Core Backend | DONE
Event Scheduler | scheduler/* (2 files) + queue server | — | EXISTS | Scheduled event triggers, cron jobs, automated status updates, reminder notifications | Sprint 2.4 - FileStorage (local + S3) | ☑ | AM - Aisha | Platform | DONE
CRM Integration | crm/hubspot | — | MISSING | HubSpot integration, contact sync, deal tracking | P3 | ☐ | SP - Sanya | Integrations | NOT STARTED
Google Calendar | googleCalender/googleCalenderService | — | MISSING | Calendar integration for delivery scheduling | P3 | ☐ | SP - Sanya | Integrations | NOT STARTED
Super Admin | superAdmin/analytics + controllers/super-admin/* | — | MISSING | Cross-store analytics, store management, campaign management, billing admin, webhook admin | P2 | ☑ | RG - Rohan | Integrations | DONE
Integration Worker | — (new) | workers/integration-worker.ts | EXISTS | Integration event processing worker exists | — | ☑ | — | — | DONE
Notification Worker | — (new) | workers/notification-worker.ts | EXISTS | Notification dispatch worker exists (shell) | — | ☑ | — | — | DONE
Optimization Worker | — (new) | workers/optimization-worker.ts | EXISTS | Route optimization worker exists (shell) | — | ☑ | — | — | DONE
Settings Management | — (none) | routes/settings.ts | EXISTS | — (all implemented) | P2 | ☑ | RG | Backend | DONE
Drivers CRUD | — (partial) | routes/drivers.ts | EXISTS | — (all implemented) | P1 | ☑ | VS | Delivery Ops | DONE
Zones CRUD | — (partial) | routes/zones.ts | EXISTS | — (all implemented) | P1 | ☑ | VS | Delivery Ops | DONE
Time Slots | — (none) | routes/time-slots.ts | EXISTS | — (all implemented) | P2 | ☑ | VS | Delivery Ops | DONE
Locations CRUD | — (none) | routes/locations.ts | EXISTS | — (all implemented) | P2 | ☑ | VS | Delivery Ops | DONE
Shipments CRUD | — (none) | routes/shipments.ts | EXISTS | — (all implemented) | P1 | ☑ | PK | Core Backend | DONE
Customers CRUD | — (none) | routes/customers.ts | EXISTS | — (all implemented) | P2 | ☑ | PK | Core Backend | DONE
Products CRUD | — (none) | routes/products.ts | EXISTS | — (all implemented) | P2 | ☑ | PK | Core Backend | DONE
Payments CRUD | — (none) | routes/payments.ts | EXISTS | — (all implemented) | P2 | ☑ | RG | Backend | DONE
Calendar Rules | — (none) | routes/calendar-rules.ts | EXISTS | — (all implemented) | P2 | ☑ | VS | Delivery Ops | DONE
Shipping Profiles | — (none) | routes/shipping-profiles.ts | EXISTS | — (all implemented) | Sprint 2.4 - FileStorage (local + S3) | ☑ | VS | Delivery Ops | DONE
Analytics | — (none) | routes/analytics.ts | EXISTS | — (all implemented) | P3 | ☑ | RG | Backend | DONE
Activity Logs | — (none) | routes/activity-logs.ts | EXISTS | — (all implemented) | P3 | ☑ | AR | Architecture | DONE
Notification Templates | — (none) | routes/notification-templates.ts | EXISTS | — (all implemented) | P2 | ☑ | SP | Integrations | DONE
Integrations | — (none) | routes/integrations.ts | EXISTS | — (all implemented) | P2 | ☑ | AM | Shopify | DONE
Organizations | — (none) | routes/orgs.ts | EXISTS | — (all implemented) | P2 | ☑ | AR | Architecture | DONE
Health Checks | — (none) | routes/health.ts | EXISTS | — (liveness + readiness + deep) | P1 | ☑ | RG | Backend | DONE
SPRINT 2.8 PLANNED
Auth Provider Registry | — (new) | packages/core/src/auth/ | PLANNED | Multi-provider auth (Auth0, Clerk, Cognito, Firebase Auth, SAML, OIDC) with same BYOK pattern as routing/notifications | P1 | ☐ | AR - Arjun
Platform Admin API | — (new) | routes/admin.ts | PLANNED | User CRUD, customer management, store oversight, platform metrics, config management | P1 | ☐ | PK - Priya
POS Integration | pos/posCustomFormService | routes/pos.ts + core/pos/ | PLANNED | POS checkout, custom form builder, POS-specific shipping profiles | P2 | ☐ | RG - Rohan
Docker Production Deploy | — (new) | infra/docker/ | PLANNED | Multi-stage Dockerfiles, docker-compose.prod.yml, health checks, env config | P1 | ☐ | AM - Aisha
API Hardening | — (existing) | routes/*.ts | PLANNED | Zod validation on all routes, error standardization, OpenAPI spec generation | P1 | ☐ | PK - Priya
E2E Test Framework | — (new) | tests/e2e/ | PLANNED | Integration test suites, load testing scripts (k6), CI pipeline | P2 | ☐ | KS - Kavitha
EVENT SYSTEM (Sprint 3.0)
Event Bus | Typed event emitter + Redis Streams pub/sub | Sprint 3.0 | Planned
Webhook API | Registration, delivery, signing, retry routes | Sprint 3.0 | Planned
Workflow Integration | Auto-trigger workflows from existing API endpoints | Sprint 3.0 | Planned
Socket.io Workflow Events | Real-time workflow progress over WebSocket | Sprint 3.0 | Planned
Shopify Workflow Bridge | Shopify order webhook → createDeliveryOrder trigger | Sprint 3.0 | Planned

## Infrastructure Gap
Component | Old System | New Platform | Status | Action Required | Priority | Done | Assignee | Squad | Work Status
Database | MongoDB (Mongoose + speed-goose caching) | PostgreSQL + Prisma 6 | EXISTS | Data migration scripts needed for existing customers | P0 | ☑ | AM - Aisha | Platform | DONE
Message Queue | Azure Service Bus (9 queues) | packages/core/src/queue/ (7 consumers + base class) | EXISTS | BullMQ consumers: order-webhook, product-webhook, driver-tracking, event-scheduler + DLQ | P0 | ☑ | AM - Aisha | Platform | DONE
Cache Layer | Redis (sessions + pub/sub + ORM cache) | packages/core/src/cache/ | EXISTS | Redis client exists but caching strategy not implemented; need: session store, query cache, rate limiting, pub/sub for real-time | P1 | ☑ | AM - Aisha | Platform | DONE
Real-time | Firebase Realtime Database + WebSocket | Socket.io realtime layer | EXISTS | Need real-time infrastructure: WebSocket/SSE server, driver location streaming, order status push to customers | P0 | ☑ | AM - Aisha | Platform | DONE
File Storage | Local + cloud (implied) | — | EXISTS | Sprint 2.4 - Local + S3 file storage | P1 | ☑ | AM - Aisha | Platform | DONE
Process Manager | PM2 (12 processes) | Single Fastify + BullMQ workers | EXISTS | Workers exist as stubs; need full implementations | Sprint 2.7 - process-manager with 4 workers | ☑ | AM - Aisha | Platform | NOT STARTED
Geospatial | Google Maps + Mapbox APIs | geo-fence.ts + address.ts | EXISTS | Re-enable PostGIS, implement geocoding service, distance matrix, route optimization API | P0 | ☑ | AM - Aisha | Platform | DONE
Email Provider | SendGrid / SMTP (via notification service) | email/providers + dispatch | EXISTS | Email sending integration, template rendering, delivery tracking | P0 | ☑ | SP - Sanya | Integrations | DONE
SMS Provider | Twilio (via smsService) | sms/providers + dispatch | EXISTS | SMS sending, delivery receipts, phone number validation | P1 | ☑ | SP - Sanya | Integrations | DONE
WhatsApp | Meta Cloud API (via whatsApp services) | — | MISSING | WhatsApp Business API: template management, message sending, webhook handling | P1 | ☑ | SP - Sanya | Integrations | DONE
Push Notifications | Firebase Cloud Messaging | push-handler.ts (FCM) | PARTIAL | FCM integration for driver app push notifications | P1 | ☑ | SP - Sanya | Integrations | DONE
Authentication | JWT + cookie sessions + Shopify session tokens | JWT + requireAuth middleware | EXISTS | Need: JWT implementation, refresh tokens, Shopify session bridge, dashboard auth middleware | P0 | ☑ | AR - Arjun | Architecture | DONE
Rate Limiting | stopcock library | — | EXISTS | Sprint 2.4 - Token bucket rate limiter | P1 | ☑ | AM - Aisha | Platform | DONE
Monitoring | Sentry + FullStory | — | EXISTS | Sprint 2.4 - MetricsCollector + HealthCheckRegistry | P2 | ☑ | AM - Aisha | Platform | DONE
CI/CD | Docker + AWS/Azure scripts | Dockerfile + CI/CD + docker-compose | EXISTS | Sprint 2.3 - GitHub Actions workflows | P1 | ☑ | AM - Aisha | Platform | DONE
Data Migration | — | packages/core/src/migration/ (mongodb-adapter, transformers, runner-v2) | EXISTS | MongoDB→PostgreSQL with idempotent upsert, checkpointing, 7 entity transformers | P0 | ☑ | PK - Priya | Core Backend | DONE
PostGIS Extension | N/A (used Google/Mapbox) | packages/core/src/spatial/ (PostGIS queries + GeoJSON types) | EXISTS | Parameterized SQL for ST_Distance, ST_Contains, ST_Within; Haversine fallback | P0 | ☑ | AM - Aisha | Platform | DONE
Cron / Scheduler | PM2 cron + event scheduler queue | — | EXISTS | Sprint 2.4 - Cron-based scheduler | P1 | ☑ | AM - Aisha | Platform | DONE
Logging | Console + implied | — | MISSING | Structured logging (Pino), log aggregation, request tracing | P2 | ☑ | AM - Aisha | Platform | DONE
Encryption | Implied for tokens | Planned for credentials | PARTIAL | Need: credential encryption at rest (Integration model), token encryption, PII protection | P1 | ☑ | AR - Arjun | Architecture | DONE
GDPR Compliance | — (none) | packages/core/src/compliance/ | EXISTS | — (anonymizer, consent, retention, audit) | P2 | ☑ | DM | Data | DONE
HMAC Webhook Verification | — (none) | middleware/hmac.ts | EXISTS | — (Shopify HMAC validation) | P1 | ☑ | RG | Backend | DONE
E2E Test Suites | — (none) | 7 test files (4,439 lines) | EXISTS | — (compliance, cache, API tests) | P2 | ☑ | KS | QA | DONE
SPRINT 2.8 PLANNED
Auth Provider Abstraction | — (new) | packages/core/src/auth/ | PLANNED | Multi-provider auth registry: Auth0, Clerk, AWS Cognito, Firebase Auth, generic OIDC, SAML 2.0 — same pattern as routing BYOK | P1 | ☐ | AR - Arjun
Docker Production Stack | Docker + Azure scripts | infra/docker/ | PLANNED | Multi-stage Dockerfiles, compose.prod.yml, Traefik reverse proxy, health checks, secrets management | P1 | ☐ | AM - Aisha
OpenAPI Spec | — (new) | docs/openapi.yaml | PLANNED | Auto-generated OpenAPI 3.1 spec from Fastify schemas, Swagger UI at /docs | P2 | ☐ | PK - Priya
DESIGN SYSTEM INFRA (Sprint 3.0)
Tailwind CSS 4 | PostCSS + Tailwind setup with --wl-* token bridge | Sprint 3.0 | Planned
shadcn/ui Registry | Component registry with Witylogix dark theme preset | Sprint 3.0 | Planned
Redis Streams | Event bus persistence layer for reliable pub/sub | Sprint 3.0 | Planned

## Priority Roadmap
Phase | Sprint | Work Item | Category | Est. Effort | Dependencies | Deliverable | Done | Assignee | Squad | Work Status
Phase 1: Foundation | 1-2 | Authentication system (JWT, login, register, password reset) | Backend + Frontend | 2 weeks | — | Auth middleware, login/register pages, session management | ☑ | AR - Arjun | Architecture | DONE
Phase 1: Foundation | 1-2 | PostGIS re-enable + geocoding service | Backend + Infra | 1 week | — | Spatial queries, point-in-polygon, distance calc | ☑ | AM - Aisha | Platform | DONE
Phase 1: Foundation | 1-2 | Shipment model + migration | Backend | 1 week | — | Prisma schema + API routes for shipments | ☑ | PK - Priya | Core Backend | DONE
Phase 1: Foundation | 2-3 | Location/Warehouse model + CRUD | Backend + Frontend | 2 weeks | PostGIS | Location management pages + API | ☑ | VS - Vikram | Core Backend | DONE
Phase 1: Foundation | 2-3 | Calendar rules + delivery rules engine | Backend | 2 weeks | — | Scheduling engine, blackout dates, time windows | ☑ | VS - Vikram | Core Backend | DONE
Phase 1: Foundation | 3-4 | Shipping profile system | Backend + Frontend | 2 weeks | Locations, Zones, Rules | Rate calculation, profile management UI | ☑ | VS - Vikram | Core Backend | DONE
Phase 2: Core Ops | 5-6 | Order CRUD (full lifecycle + manual creation) | Backend + Frontend | 2 weeks | Auth | Order create page, detail page, status management | ☑ | PK - Priya | Core Backend | DONE
Phase 2: Core Ops | 5-6 | Shipment lifecycle (create, track, deliver) | Backend + Frontend | 3 weeks | Shipment model, Orders | Shipment pages, status transitions, POD | ☑ | PK - Priya | Core Backend | DONE
Phase 2: Core Ops | 6-7 | Route optimization (Mapbox/Google integration) | Backend | 2 weeks | PostGIS, Drivers | Distance matrix, route optimization API | ☑ | VS - Vikram | Core Backend | DONE
Phase 2: Core Ops | 7-8 | Route creation + editing UI | Frontend | 2 weeks | Route optimization | Route create/edit pages with map + drag/drop | ☑ | DM - Dev | Frontend | DONE
Phase 2: Core Ops | 7-8 | Webhook processing (order, product, customer, inventory) | Backend | 2 weeks | BullMQ | Queue consumers for each Shopify webhook type | ☑ | PK - Priya | Core Backend | DONE
Phase 2: Core Ops | 8-9 | Shopify sync engine (orders, products, customers, inventory) | Backend | 3 weeks | Webhooks, Models | Full bidirectional Shopify sync | ☑ | PK - Priya | Core Backend | DONE
Phase 3: Comms | 10-11 | Email dispatch (SendGrid/SMTP) | Backend | 1 week | — | Email sending service + template rendering | ☑ | SP - Sanya | Integrations | DONE
Phase 3: Comms | 10-11 | SMS dispatch (Twilio) | Backend | 1 week | — | SMS sending service | ☑ | SP - Sanya | Integrations | DONE
Phase 3: Comms | 11-12 | WhatsApp integration (Meta Cloud) | Backend | 2 weeks | — | WhatsApp template sync + message dispatch | ☑ | SP - Sanya | Integrations | DONE
Phase 3: Comms | 11-12 | Push notifications (Firebase) | Backend | 1 week | — | FCM integration for driver app | ☑ | SP - Sanya | Integrations | DONE
Phase 3: Comms | 12-13 | Notification template editor | Frontend | 2 weeks | Email service | Unlayer email editor, template management UI | ☑ | SP - Sanya | Integrations | DONE
Phase 3: Comms | 12-13 | Real-time driver tracking | Backend + Frontend | 2 weeks | Firebase/WebSocket | Live driver location on dashboard maps | ☑ | PAIR | Cross-team | DONE
Phase 4: Commerce | 14-15 | Product + Customer models + sync | Backend | 2 weeks | Shopify sync | Product catalog, customer database | ☑ | PK - Priya | Core Backend | DONE
Phase 4: Commerce | 14-15 | Payment processing (COD + gateway) | Backend | 2 weeks | Orders, Shipments | Payment gateway, COD, transaction tracking | ☑ | RG - Rohan | Integrations | DONE
Phase 4: Commerce | 15-16 | Carrier rate calculation engine | Backend | 2 weeks | Shipping profiles | Multi-carrier comparison, Shopify carrier callback | ☑ | VS - Vikram | Core Backend | DONE
Phase 4: Commerce | 15-16 | Cart plugin / storefront widget | Backend + Frontend | 2 weeks | Rates, Time slots | Checkout date picker, rate display widget | ☑ | DM - Dev | Frontend | DONE
Phase 4: Commerce | 16-17 | Inventory tracking system | Backend | 2 weeks | Products, Locations | Inventory by location, reorder points, sync | ☑ | PK - Priya | Core Backend | DONE
Phase 5: Admin | 18-19 | Analytics engine + dashboard data | Backend + Frontend | 2 weeks | Orders, Shipments | Time-series aggregation, chart data APIs | ☑ | RG - Rohan | Integrations | DONE
Phase 5: Admin | 18-19 | Billing & plans system | Backend + Frontend | 2 weeks | Shopify billing API | Plan catalog, usage metering, upgrade flow | ☑ | RG - Rohan | Integrations | DONE
Phase 5: Admin | 19-20 | Audit trail / history system | Backend | 1 week | — | Activity logging, entity change tracking | ☑ | AR - Arjun | Architecture | DONE
Phase 5: Admin | 19-20 | User invitation + RBAC | Backend + Frontend | 2 weeks | Users model | Invite flow, role assignment, permissions matrix | ☑ | AR - Arjun | Architecture | DONE
Phase 5: Admin | 20-21 | Onboarding flow | Frontend | 2 weeks | Auth, Shipping profiles | Multi-step setup wizard | ☑ | NK - Neha | Frontend | DONE
Phase 5: Admin | 20-21 | Super admin panel | Backend + Frontend | 2 weeks | All models | Cross-store management, billing admin | ☑ | RG - Rohan | Integrations | DONE
Phase 6: Polish | 22-23 | Campaign / marketing module | Backend + Frontend | 2 weeks | Notifications | Campaign creation, audience targeting, broadcast | ☑ | SP - Sanya | Integrations | DONE
Phase 6: Polish | 22-23 | Custom metafields system | Backend + Frontend | 1 week | — | Custom field definitions, per-entity data | ☑ | PK - Priya | Core Backend | DONE
Phase 6: Polish | 23-24 | POS integration | Backend | 2 weeks | Products, Payments | POS checkout, custom forms | ☐ | RG - Rohan | Integrations | NOT STARTED
Phase 6: Polish | 23-24 | Map views (orders, shipments, routes on map) | Frontend | 2 weeks | PostGIS, Leaflet | Leaflet map components with marker clusters | ☑ | DM - Dev | Frontend | DONE
Phase 6: Polish | 24-25 | Data migration tools (MongoDB → PostgreSQL) | Backend | 3 weeks | All models | Migration scripts, validation, rollback | ☑ | PK - Priya | Core Backend | DONE
Phase 6: Polish | 24-25 | CI/CD, Docker, monitoring | Infra | 2 weeks | — | Docker builds, Sentry, Pino logging, deployment | ☑ | AM - Aisha | Platform | DONE
SPRINT 2.8 PLANNED
Phase 7: Production | 2.8 | Auth provider abstraction (Auth0, Clerk, Cognito, Firebase, OIDC, SAML) | Backend + Infra | 2 weeks | Auth system | Multi-provider auth registry with BYOK pattern | ☐
Phase 7: Production | 2.8 | Platform admin panel (user/customer management) | Backend + Frontend | 2 weeks | Auth, RBAC | Admin dashboard for platform-level oversight | ☐
Phase 7: Production | 2.8 | Activity log & Settings redesign (frontend-design) | Frontend | 1 week | Audit, Settings | Production-grade UI with frontend-design skill | ☐
Phase 7: Production | 2.8 | Docker production deployment | Infra | 1 week | — | Multi-stage Dockerfiles, compose.prod.yml, health checks | ☐
Phase 7: Production | 2.8 | POS integration | Backend | 2 weeks | Products, Payments | POS checkout, custom forms | ☐
Phase 7: Production | 2.8 | API hardening + OpenAPI spec | Backend | 1 week | All routes | Zod validation, error standardization, Swagger UI | ☐
Phase 7: Production | 2.8 | E2E tests + load testing | QA | 1 week | All apps | Integration suites, k6 load tests, CI pipeline | ☐
PHASE 3.0: EVENT SYSTEM & DESIGN SYSTEM
Design System Migration | Migrate dashboard from custom components to shadcn/ui + Tailwind CSS 4 | Phase 3.0 | Sprint 3.0-3.1 | CRITICAL
Component Library (shadcn/ui) | Install and configure shadcn/ui with Witylogix theme tokens | Phase 3.0 | Sprint 3.0 | HIGH
Tailwind CSS 4 Setup | Add Tailwind CSS 4 to dashboard with --wl-* token mapping | Phase 3.0 | Sprint 3.0 | HIGH
Event Bus Foundation | Typed event emitter with Redis Streams pub/sub | Phase 3.0 | Sprint 3.0 | HIGH
Workflow-API Integration | Wire workflow engine into existing order/driver/delivery endpoints | Phase 3.0 | Sprint 3.0 | HIGH
Webhook System | Outbound webhooks for workflow events with signing and retry | Phase 3.0 | Sprint 3.0 | MEDIUM
Real-time Workflow Updates | Socket.io integration for live workflow step progression | Phase 3.0 | Sprint 3.0 | MEDIUM
Shopify Workflow Triggers | Connect Shopify order webhooks to workflow engine | Phase 3.0 | Sprint 3.0 | MEDIUM
SPRINT 3.1 PLANNED
SPRINT 3.2 PLANNED — Notification Providers, Carrier APIs, POS Extension & Page Migration (Date: 2026-03-08)
Phase 3.2: Notifications & Carriers | 3.2 | ADR-012 notification architecture + orchestrator wiring | Backend | — | — | 3 files | ☐ | AR - Arjun | Architecture | PLANNED
Phase 3.2: Notifications & Carriers | 3.2 | Page Tailwind migration batch 4 — orders/*, routes/* | Frontend | — | — | 10 pages | ☐ | DM - Dev | Frontend | PLANNED
Phase 3.2: Notifications & Carriers | 3.2 | Page Tailwind migration batch 5 — delivery/*, shipping-profiles/*, collections, integrations | Frontend | — | — | 8 pages | ☐ | NK - Neha | Frontend | PLANNED
Phase 3.2: Notifications & Carriers | 3.2 | SendGrid + Twilio real HTTP implementations | Backend | — | — | 2 files | ☐ | RG - Rohan | Integrations | PLANNED
Phase 3.2: Notifications & Carriers | 3.2 | WhatsApp + Firebase Push real HTTP implementations | Backend | — | — | 2 files | ☐ | SP - Sanya | Integrations | PLANNED
Phase 3.2: Notifications & Carriers | 3.2 | Page Tailwind migration batch 6 — analytics, billing, support, profile, notifications, stores | Frontend | — | — | 6 pages | ☐ | VS - Vikram | Core Backend | PLANNED
Phase 3.2: Notifications & Carriers | 3.2 | FedEx + UPS carrier adapter real HTTP APIs | Backend | — | — | 2 files | ☐ | PK - Priya | Core Backend | PLANNED
Phase 3.2: Notifications & Carriers | 3.2 | Notification provider tests + carrier adapter tests + validator tests | QA | — | — | 6 test suites | ☐ | KS - Kavitha | QA | PLANNED
Phase 3.2: Notifications & Carriers | 3.2 | POS UI extension scaffold + checkout/POS shared components | Backend + Frontend | — | — | 8 files | ☐ | AM - Aisha | Platform | PLANNED
SPRINT 3.3 PLANNED — Worker Wiring, Auth OAuth2, OSRM Routing & Final Page Migration (Date: 2026-03-08)
Phase 3.3: Worker & Auth | 3.3 | ADR-013 worker-orchestrator architecture + notification worker rewrite to use orchestrator | Backend | — | —
Phase 3.3: Worker & Auth | 3.3 | Page Tailwind migration batch 7 — map, tracking/live, onboarding, widget-config, time-slots | Frontend | — | —
Phase 3.3: Worker & Auth | 3.3 | Page Tailwind migration batch 8 — auth/login, auth/register, auth/forgot-password, auth/layout, campaigns, campaigns/[id] | Frontend | — | —
Phase 3.3: Worker & Auth | 3.3 | DHL carrier adapter real HTTP + OSRM Phase 2 routing provider | Backend | — | —
Phase 3.3: Worker & Auth | 3.3 | Auth OAuth2 code exchange + API route BullMQ job wiring | Backend + Frontend | — | —
Phase 3.3: Worker & Auth | 3.3 | Page Tailwind migration batch 9 — page.tsx (home), widgets, routes/[id]/assign, admin/design-system, onboarding/layout, layout.tsx | Frontend | — | —
Phase 3.3: Worker & Auth | 3.3 | Notification worker integration tests + API route notification enqueueing | Backend | — | —
Phase 3.3: Worker & Auth | 3.3 | Validator schema tests + carrier adapter DHL tests + OSRM routing tests | QA | — | —
Phase 3.3: Worker & Auth | 3.3 | Shopify app webhook integration + checkout extension improvements | Backend + Frontend | — | —
SPRINT 3.4 PLANNED — Platform Abstraction, Competitive Intel & Final Tailwind Migration (Date: 2026-03-08)
Phase 3.4: Platform Abstraction | 3.4 | Fleetbase competitive analysis + ADR-014 platform abstraction | Backend | — | — | 3 files | ☐ | AR - Arjun | Architecture | PLANNED
Phase 3.4: Platform Abstraction | 3.4 | Page Tailwind migration batch 10 — stores, tracking-config, admin/shops/[id], profile, activity | Frontend | — | — | 5 pages, ~450 style conversions | ☐ | DM - Dev | Frontend | PLANNED
Phase 3.4: Platform Abstraction | 3.4 | Page Tailwind migration batch 11 — drivers, calendar, notifications, admin/customers, shipments | Frontend | — | — | 5 pages, ~315 styles | ☐ | NK - Neha | Frontend | PLANNED
Phase 3.4: Platform Abstraction | 3.4 | Platform source abstraction — Prisma schema + queue types + consumer refactor | Backend | — | — | 6 files | ☐ | RG - Rohan | Core Backend | PLANNED
Phase 3.4: Platform Abstraction | 3.4 | Workflow platform abstraction + API route TODO stubs | Backend + Frontend | — | — | 5 files | ☐ | SP - Sanya | Integrations | PLANNED
Phase 3.4: Platform Abstraction | 3.4 | Page Tailwind migration batch 12 — admin/workflows/[id], widget-config, shipping-profiles, admin/workflows, locations, admin/users | Frontend | — | — | 6 pages, ~176 styles | ☐ | VS - Vikram | Frontend | PLANNED
Phase 3.4: Platform Abstraction | 3.4 | Analytics events DI injection + billing Shopify subscription status | Backend | — | — | 4 files | ☐ | PK - Priya | Core Backend | PLANNED
Phase 3.4: Platform Abstraction | 3.4 | Platform abstraction tests + regression tests for refactored consumers | QA | — | — | 4 test suites | ☐ | KS - Kavitha | QA | PLANNED
Phase 3.4: Platform Abstraction | 3.4 | Collections platform abstraction + collections Shopify GraphQL adapter | Backend + Frontend | — | — | 4 files | ☐ | AM - Aisha | Platform | PLANNED
Phase 3: Competitive Parity
Phase 3: Competitive Parity | 4.5 | Route Timeline Dispatcher Dashboard | Frontend + Backend | 2 weeks | Event Bus, Route Optimization | Routific-quality dispatch view with color-coded routes + timeline | ☐ | AR - Arjun | Architecture | PLANNED
Phase 3: Competitive Parity | 4.5 | Checkout Date/Time Picker Widget | Frontend + Package | 2 weeks | Slot Engine API | Pickeasy-quality embeddable widget with slots, blackout, zip validation | ☐ | NK - Nikhil | Frontend | PLANNED
Phase 3: Competitive Parity | 4.5 | Customer Self-Service Portal | Frontend (New App) | 2 weeks | Auth, Orders API | Next.js portal: order history, tracking, reschedule, preferences | ☐ | DM - Deepak | Frontend | PLANNED
Phase 3: Competitive Parity | 4.5 | Slot Engine API & Capacity Management | Backend | 1.5 weeks | Prisma models | Slot availability, capacity limits, zone-rate calculator, deadlines | ☐ | RG - Rahul | Core Backend | PLANNED
Phase 3: Competitive Parity | 4.5 | POD v2: Photo + Signature + QR | Backend + Mobile | 2 weeks | S3/R2 storage | Multi-method POD with delivery status timeline + cloud storage | ☐ | PK - Priya | Core Backend | PLANNED
Phase 3: Competitive Parity | 4.5 | Customer Notification Engine v2 | Backend + Integration | 2 weeks | Twilio, Meta Business | Email + SMS + WhatsApp + push with template engine | ☐ | SP - Sanjay | Full-stack | PLANNED
Phase 3: Competitive Parity | 4.5 | Checkout & Dispatch Component Library | Frontend | 1.5 weeks | Design system | DatePicker, TimeSlotGrid, RouteTimeline, DriverCard, StopMarker | ☐ | VS - Vikram | Frontend | PLANNED
Phase 3: Competitive Parity | 4.5 | E2E: Dispatch, Checkout & Portal | QA | 2 weeks | All Sprint 4.5 features | Playwright suites for dispatch, checkout, portal, POD, notifications | ☐ | KS - Kavitha | QA | PLANNED
Phase 3: Competitive Parity | 4.5 | Shopify Checkout Extension + Google Maps | Integration | 2 weeks | Checkout widget | Shopify extension, Google Maps zone viz, Calendar sync | ☐ | AM - Aisha | Platform | PLANNED
Phase 3: Competitive Parity | 4.5 | Smart Slot Recommendation + ML ETA | AI/ML | 2 weeks | Slot Engine, historical data | ML slot recommender + traffic-aware ETA (3-5 models) | ☐ | ZR - Zara | AI | PLANNED
Phase 3: Competitive Parity | 4.6 | WooCommerce Deep Integration | Integration | 2 weeks | Checkout widget, Orders API | WooCommerce REST API adapter, checkout block, webhook sync | ☐ | AM - Aisha | Platform | PLANNED
Phase 3: Competitive Parity | 4.6 | Google Maps & Calendar Native Integration | Integration | 1 week | Maps JS API | Zone visualization, address autocomplete, Calendar order reminders | ☐ | NK - Nikhil | Frontend | PLANNED
Phase 3: Competitive Parity | 4.6 | Planned-vs-Actual Reporting | Analytics | 2 weeks | GPS tracking, Route data | Route analytics, on-time %, driver scorecard, CO2 tracking | ☐ | AR - Arjun | Architecture | PLANNED
Phase 3: Competitive Parity | 4.7 | Telematics Gateway (Samsara + Geotab) | Integration + Backend | 3 weeks | Fleet module | Adapter layer for Samsara, Geotab, Verizon, Motive | ☐ | AM - Aisha | Platform | PLANNED
Phase 3: Competitive Parity | 4.7 | ML-Powered ETA Engine (Traffic-Aware) | AI/ML | 3 weeks | Google Directions API | Traffic-aware ETA with 3-5 ML models, fallback to statistical | ☐ | ZR - Zara | AI | PLANNED
Phase 3: Competitive Parity | 4.8 | Partner Directory & Courier Ecosystem | Integration | 3 weeks | Courier API adapters | Onfleet, Stuart, Uber Direct adapters + partner directory | ☐ | AM - Aisha | Platform | PLANNED
Phase 3: Competitive Parity | 4.9 | Automated Invoicing Engine | Backend | 2 weeks | Orders, Billing module | Per-delivery/route invoicing, PDF generation, QuickBooks/Xero | ☐ | RG - Rahul | Core Backend | PLANNED
Phase 4: Market Leadership | 5.0 | AI Demand Prediction & Smart Scheduling | AI/ML | 4 weeks | Historical delivery data | Time-series demand forecasting, auto capacity adjustment | ☐ | ZR - Zara | AI | PLANNED

## Statistics
Gap Statistics Summary | [25 empty] | Sprint 4.5 | Sprint 4.6 | Sprint 4.7
Sprint 4.8
SPRINT PROGRESS (as of Sprint 4.5) | SPRINT PROGRESS (as of Sprint 4.7) | [24 empty] | Customer Experience & Checkout |  |  | 2600
Last Updated: Sprint 4.5 (2026-03-11) | Last Updated: Sprint 4.7 (2026-03-11) | [24 empty] | 1 (customer-portal) |  |  | 883700
Metric | Sprint 1.1 | Sprint 1.2 | Sprint 2.0 | Sprint 2.1 | Sprint 2.3 | Sprint 2.4 | Sprint 2.5 | Sprint 2.6 | Sprint 2.7 | Sprint 2.8 | Sprint 2.9 | Sprint 3.0 | Sprint 3.1 | Sprint 3.3 | Sprint 3.4 | Sprint 3.5 | Sprint 3.6 | Sprint 3.7 | Sprint 3.8 | Sprint 3.9 | Sprint 4.0 | Sprint 4.1 | Sprint 4.2 | Sprint 4.3 | Sprint 4.4 | Sprint 4.5 | 3280 | 2467 | 94
Source Files | 184 | 258 | 325 | 418 | 429 | 461 | 512 | 555 | 794 | 848 | 1565 | 1609 | 1700 | 1800 | 1860 | 1900 | 1960 | 2000 | 2050 | 2100 | 2200 | 2280 | 2320 | 2343 | 2410 | 2593 | 803280 | 845846 | 146
Lines of Code | 22541 | 40672 | 58339 | 83232 | 113346 | 130966 | 153011 | 168753 | 208287 | 221000 | 156361 | 170399 | 200000 | 225000 | 235000 | 248000 | 262000 | 280000 | 298000 | 320000 | 350000 | 371000 | 383000 | 392000 | 423000 | 468604 | 80 | 88 | 483
Dashboard Pages | 10 | 14 | 18 | 24 | 37 | 47 | 50 | 50 | 57 | 64 | 65 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 70 | 70 | 74 | 76 | 133 | 138 | 41
API Routes | 8 | 12 | 18 | 25 | 27 | 39 | 42 | 44 | 51 | 55 | 63 | 67 | 75 | 75 | 70 | 71 | 73 | 73 | 73 | 73 | 73 | 73 | 74 | 74 | 75 | 83 | 107 | 39
Prisma Models | 18 | 22 | 26 | 30 | 32 | 34 | 26 | 25 | 28 | 30 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 35 | 37 | 65 | 70
Core Modules | 4 | 6 | 8 | 12 | 18 | 32 | 38 | 43 | 48 | 51 | 51 | 57 | 62 | 66 | 68 | 72 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 80 | 90 | 247 | 266
Test Files | 0 | 0 | 0 | 0 | 22 | 29 | 37 | 44 | 51 | 57 | 63 | 69 |  |  | 73 | 77 | 85 | 99 | 114 | 139 | 180 | 180 | 190 | 191 | 205 | 127 | 280 | 310
Shopify Pages | [12 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 2800 | 3300
Test Suites | [12 empty] | 75 | 85 | 89 | 93 | 101 | 115 | 130 | 155 | 180 | 180 | 190 | 191 | 205 | 210 | 73 | 73
Test Cases | [12 empty] | 250 | 280 | 310 | 434 | 844 | 1763 | 2534 | 3808 | 4676 | 4676 | 4817 | 4817 | 4900 | 2100 | 55 | 70
Workers/Consumers | Deliverable | Files | Lines | Status | [8 empty] | 8 | 8 | 8 | 9 | 12 | 12 | 12 | 12 | 12 |  |  | 12 | 12 |  | 3 | 3
Real-time Channels | Route optimization engine (3 algorithms + ETA) | 7 | 1610 | DONE | [8 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 |  | 1 | 1
Workflow Definitions | Shipping profiles detail, route assign, local orders pages | 3 | 1572 | DONE | [8 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | 10 | 10 |  | 1 | 1
Queue Types | Cart plugin components (date picker, time slots, rates) | 5 | 1817 | DONE | [8 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 |  | 1 | 1
RG - Rohan | Queue consumers (4 types) + spatial queries module | 10 | 3813 | DONE | [22 empty] | 1 | 1
SP - Sanya | Payment processing (gateway + processor + Prisma) | 6 | 2689 | DONE | [22 empty] | 1 | 1
VS - Vikram | Shipping profiles core (rate calc, calendar, validator) | 6 | 3068 | DONE | [22 empty] | 15 | 15
PK - Priya | Analytics engine (event tracker, aggregator, dashboard) | 6 | 2275 | DONE | [22 empty] | 1 | 1
KS - Kavitha | 8 test suites (optimizer, payments, analytics, queue, etc.) | 8 | 5184 | DONE | [22 empty] | 25 | 26
AM - Aisha | Migration framework + location management API | 5 | 1914 | DONE | [22 empty] | 14 | 14
[27 empty] | 11 | 13
SPRINT 2.6 DELIVERABLES
PK - Priya | Campaign, messaging, audit, permissions API routes | 4 | 2469 | DONE
KS - Kavitha | 7 test suites (RBAC, audit, dispatcher, crypto, etc.) | 7 | 4725 | DONE
AM - Aisha | Shopify campaigns, templates, audit log routes | 5 | 1628 | DONE
SPRINT 2.7 DELIVERABLES
VS - Vikram | Saved views engine + widget manager core modules | 6 | 1566 | DONE
PK - Priya | 6 API routes (billing, support, features, views, widgets, collections) | 7 | 2708 | DONE
KS - Kavitha | 7 test suites (subscription, quota, collections, support, views, widgets, process) | 7 | 3930 | DONE
AM - Aisha | 5 Shopify routes (billing, invoices, support, support detail, collections) | 5 | 2233 | DONE
SPRINT 2.8 DELIVERABLES
|  |  |  | Remaining | % Complete
VS - Vikram | Standard delivery workflow pages | 2 | 600
PK - Priya | Docker production stack (multi-stage, compose, nginx) | 5 | 800
KS - Kavitha | 6 test suites (auth, POS, errors, rate limit, validator, admin) | 6 | 1800
AM - Aisha | 3 Shopify routes (auth-providers, POS index, POS detail) | 3 | 900
SPRINT 2.9 DELIVERABLES
Agent | Deliverable | Files | Lines
AR - Arjun | Workflow engine (DI container, step runner, compensation, registry, hooks) | 10 | 3100
DM - Dev | Workflow executions list page (StatCards, filters, search, table) | 1 | 462
NK - Neha | Workflow execution detail page (step timeline, JSON viewer, retry) | 1 | 701
RG - Rohan | 3 workflow definitions (createDeliveryOrder, assignDriver, completeDelivery) | 6 | 4300
SP - Sanya | 12 reusable workflow steps (validation, geocoding, rating, assignment, etc.) | 9 | 2439
VS - Vikram | BullMQ durable execution (queue, worker, scheduler, DLQ) | 6 | 1397
PK - Priya | 4 workflow API route files (orders, drivers, delivery, executions) | 4 | 1660
KS - Kavitha | 6 test suites (engine, container, step-runner, 3 workflow tests) | 6 | 3194
AM - Aisha | ADR-009 + Architecture debate (blue/red team standup) | 2 | 800
COMPLETION SUMMARY
Category | Total Items | 31 | 72.1%
Data Models | 43 | 66 | 169.2%
Feature Pages | 39 | 67 | 167.5%
API Services | 40 | 63 | 157.5%
Infrastructure | 24 | 38 | 90.5%
Roadmap Items | 42 | 35 | 83.3%
SPRINT 3.0 PLANNED
Agent | Deliverable | Focus | Category
AR - Arjun | Event bus + ADR-010 event architecture | Backend | Architecture
DM - Dev | shadcn/ui migration Phase 1 (Button, Card, Badge, Input, Select, Modal) | Frontend | Design System
NK - Neha | shadcn/ui migration Phase 2 (Table, Tabs, Toast, StatCard, EmptyState) | Frontend | Design System
RG - Rohan | Workflow-API integration (wire workflows into existing endpoints) | Backend | Integration
SP - Sanya | Webhook system (registration, signing, retry, delivery tracking) | Full-stack | Events
VS - Vikram | Tailwind CSS 4 + design tokens bridge (--wl-* → Tailwind) | Frontend | Design System
PK - Priya | Socket.io workflow events + real-time step progression | Backend | Events
KS - Kavitha | Integration tests + component visual regression tests | QA | Testing
AM - Aisha | Shopify workflow triggers + webhook management UI | Integration | Shopify
SPRINT 3.0 DELIVERABLES
Agent | Deliverable | Files | Lines | Status
AR - Arjun | TypedEventBus (Redis Streams + InMemory), ADR-010 | 7 | 2873 | DONE
DM - Dev | shadcn/ui Phase 1: button, card, badge, input, select, modal + Tailwind config | 9 | 546 | DONE
NK - Neha | shadcn/ui Phase 2: table, tabs, toast, stat-card, empty-state + dropdown/skeleton/tooltip | 8 | 866 | DONE
RG - Rohan | Workflow-API integration (auto-trigger, hooks, Fastify plugin) | 4 | 1348 | DONE
SP - Sanya | Outbound webhook system (manager, delivery, processor, emitter, routes, Prisma) | 8 | 2186 | DONE
VS - Vikram | Design system foundation (tokens, header/sidebar migration, barrel export, gallery) | 5 | 1255 | DONE
PK - Priya | Socket.io realtime workflow events + SSE fallback + plugin | 5 | 1208 | DONE
KS - Kavitha | 6 test suites (event-bus, webhook, workflow-integration, realtime, UI, routes) | 6 | 2183 | DONE
AM - Aisha | Shopify webhook management (API handler, config, detail, event picker) | 4 | 1884 | DONE
SPRINT 3.1 PLANNED
Agent | Deliverable | Focus | Category
AR - Arjun | ADR-011, extension-core package | 8 files | Extensions
DM - Dev | Page migration batch 1 (Tailwind) | 7 pages | Design System
NK - Neha | Page migration batch 2 (Tailwind) | 7 pages | Design System
VS - Vikram | Page migration batch 3 (Tailwind) | 6 pages | Integration
RG - Rohan | Queue consumer DB integration | 4 files | Events
SP - Sanya | Event-webhook bridge | 5 files | Design System
PK - Priya | File storage + push notifications | 8 files | Infrastructure
KS - Kavitha | Integration tests | 6 test suites | Testing
AM - Aisha | Checkout UI extension | 10 files | Shopify
TOTAL | Sprint 3.1 Deliverables | 58 files + 6 test suites | 24,767 lines

## Standup Notes & Actions
WITYLOGIX — STANDUP NOTES & ACTION ITEMS
Architecture Pivot Debate — 2026-03-07 ¦ Sprint 2.9 Kickoff
Sprint 4.0 Standup — 2026-03-10 — Documentation Engine Discussion
Docs Engine | Fumadocs (Next.js, open-source, MDX, AI-ready)
Location
AI Search | Anthropic Claude API for RAG-powered doc chat
API Reference | Auto-generated from OpenAPI 3.0 spec | Scope | Key Deliverables | Status
TypeScript SDK | packages/sdk auto-generated from OpenAPI | Workflow Engine ONLY | packages/framework/, 3 core workflows (createDeliveryOrder, assignDriver, completeDelivery), BullMQ backing | Sprint 2.9 — In Progress
Design | Dark-first, --wl-* CSS vars, industrial aesthetic | Event Bus | Redis-backed event bus, notification/analytics/webhook subscribers, event-driven side effects | Deferred
Component Gallery | 23 components with live previews | Module Links + Plugin System | defineLink cross-module relations, plugin API (modules+workflows+hooks+subscribers as npm packages) | Deferred
Target | Sprint 4.1 — all 9 agents
BLUE/RED TEAM CONSENSUS
Agreement | Blue Team Position | Red Team Position | Resolution
BYOK Pattern | Keep it | Keep it | Unanimous — BYOK stays
Prisma ORM | Keep it (no DML/MikroORM) | Keep it | Unanimous — Prisma stays
Fastify Framework | Keep it | Keep it | Unanimous — Fastify stays
RLS Multi-tenancy | Keep it | Keep it | Unanimous — RLS stays
Workflow Engine | Build NOW in Sprint 2.9 | Defer until pain is proven | Blue won — build NOW, prove on 3 workflows
Event Bus | Build in Phase 1 | Defer until 10 customers | Red won — defer to Phase 2
Module Links | Build in Phase 2 | Defer until 50 customers | Red won — defer to Phase 3
Plugin System | Build in Phase 2 | Defer until customer demand | Red won — defer to Phase 3
18-Month Roadmap | Commit to full timeline | Re-evaluate after each phase | Red won — no timeline commitment
SPRINT 2.9 ACTION ITEMS
ID | Owner | Squad | Action | Deliverable | Sprint | Status
1 | AR - Arjun | Architecture | Design packages/framework/ with workflow engine, container DI, step runner | Workflow engine framework (10 files, 1,738 lines) | 2.9 | Done
2 | RG - Rohan | Core Backend | Define interfaces for WorkflowStep, WorkflowContext, StepCompensation | Workflow steps library (12 steps, 2,413 lines) | 2.9 | Done
3 | PK - Priya | Core Backend | Implement createDeliveryOrderWorkflow as proof-of-concept | 9-step workflow with 3-step compensation (1,496 lines) | 2.9 | Done
4 | SP - Sanya | Core Backend | Implement assignDriverWorkflow using the framework | 10-step workflow with scoring algorithm (1,239 lines) | 2.9 | Done
5 | NK - Neha | Core Backend | Implement completeDeliveryWorkflow | 11-step workflow with POD verification (1,576 lines) | 2.9 | Done
6 | KS - Kavitha | QA | Write test suites for all 3 workflows (step + workflow level) | 6 test files, 240+ test cases (3,194 lines) | 2.9 | Done
7 | DM - Dev | Frontend | Dashboard page: workflow execution viewer | List + detail pages with step timeline (1,163 lines) | 2.9 | Done
8 | VS - Vikram | Core Backend | Refactor 3 existing API routes to call workflows | 4 workflow route files (1,660 lines) | 2.9 | Done
9 | AM - Aisha | Platform | BullMQ integration for durable workflow execution | Queue, worker, scheduler, dead-letter (1,397 lines) | 2.9 | Done
10 | ALL | ALL | After Sprint 2.9: review, retrospective, decide Phase 2 scope | Retrospective document | 3.0 | Planned
REFERENCE DOCUMENTS
ADR-009: | docs/adr/ADR-009-medusa-inspired-architecture-evolution.md
Standup Notes: | docs/sprint-notes/STANDUP-2026-03-07-architecture-debate.md
Blue Team: | AR (CTO), DM (Frontend), NK (Frontend Lead), KS (QA Lead)
Red Team: | RG (Backend Lead), SP (Full-stack), PK (Sr. Backend), VS (Component Dev), AM (Integration)
Sprint 4.2 Standup — 2026-03-10
Sprint 4.2 shipped: ADR-021, SDK tests (141 cases), seed script, driver app screens, settings page, webhook dashboard, 5 new UI components, smoke test, CI updates
Deep dive: CLI deployment tool for one-line VM deployment
Decision: Pure bash CLI (witylogix) with 12 subcommands — install, deploy, upgrade, status, logs, backup, restore, ssl, env, doctor, scale, destroy
Decision: Caddy for reverse proxy with auto-SSL (api/app/docs subdomain routing)
Decision: AI subcommands (ai setup, ai diagnose) for Claude-powered diagnostics
NEW TEAM MEMBER: ZR — Zara (AI Engineer) — AI-powered features, docs search, CLI diagnostics, log analysis
Sprint 4.3 planned: Full CLI tool (infra/cli/witylogix), Caddy templates, production Docker Compose, AI diagnostics, CLI tests

## Sprint 3.5 Plan
Sprint 3.5 — TODO Cleanup, Platform Abstraction Phase 2, WooCommerce Adapter & Final Tailwind Push
Agent | Deliverable | Files (est) | Lines (est) | Status
AR - Arjun | ADR-015 WooCommerce integration + adapter architecture | 3 | 1200 | PLANNED
RG - Rohan | Platform abstraction Phase 2 (workflow-integration, inventory, integrations) | 6 | 1800 | PLANNED
SP - Sanya | TODO stub cleanup — API routes (routes.ts, collections.ts, integration-worker) | 4 | 800 | PLANNED
PK - Priya | TODO stub cleanup — Core modules (campaigns, event-bus, notifications, orchestrator) | 5 | 600 | PLANNED
DM - Dev | Tailwind migration batch 13: drivers (76 styles), onboarding (73 styles) | 2 | 1400 | PLANNED
NK - Nisha | Tailwind migration batch 14: shipping-profiles, locations, admin, register | 4 | 1200 | PLANNED
VS - Vikram | Tailwind migration batch 15: inventory, login, admin/customers, delivery, forgot-password | 5 | 1000 | PLANNED
KS - Kavitha | Test suites: WooCommerce adapter, TODO-fix integration, workflow platform tests | 4 | 2800 | PLANNED
AM - Aisha | WooCommerce webhook consumer + REST API adapter (orders/products/inventory) | 5 | 2000 | PLANNED
TOTALS

## Sprint 3.6 Plan
Sprint 3.6 — Magento Adapter, API Route Tests, Platform Cleanup & Tailwind Finish
Agent | Deliverable | Files (est) | Lines (est) | Status
AR - Arjun | ADR-016 Magento integration + Magento REST adapter (PlatformAdapter) | 3 | 1800 | PLANNED
RG - Rohan | Platform abstraction Phase 3 — final Shopify refs in payments, integrations, collections | 6 | 600 | PLANNED
SP - Sanya | API route integration tests: orders, drivers, routes, webhooks | 4 | 3200 | PLANNED
PK - Priya | Final 2 TODO stubs cleanup + Magento webhook consumer | 3 | 800 | PLANNED
DM - Dev | Tailwind batch 16: admin, widgets, delivery/standard, campaigns/[id], design-system | 5 | 1200 | PLANNED
NK - Nisha | Tailwind batch 17: register, shipping-profiles/[id], shipments, page.tsx, auth/layout | 5 | 1200 | PLANNED
VS - Vikram | Tailwind batch 18: integrations, stores, payments, admin/shops/[id], activity | 5 | 1000 | PLANNED
KS - Kavitha | Platform adapter unit tests: Shopify, WooCommerce, Magento, registry | 4 | 3600 | PLANNED
AM - Aisha | Custom platform adapter (API key auth, field mapping) + generic webhook route | 4 | 1600 | PLANNED
TOTALS

## Sprint 3.7 Plan
Sprint 3.7 Plan — Auth Actions, Core Tests, Shopify TODOs & Deep Tailwind
Agent | Assignee | Task | Deliverables | Est. Lines | Priority
AR (CTO) | Arjun | ADR-017 + Auth Actions Architecture | ADR-017 auth-actions design, dashboard auth-actions.ts real implementation (login/register/forgot-password with API client) | ~800 | P0
RG (Backend Lead) | Rohan | Core module tests: tracking, labels, monitoring | tracking/__tests__/*.test.ts, labels/__tests__/*.test.ts, monitoring/__tests__/*.test.ts | ~2,400 | P0
SP (Full-stack) | Sanya | Core module tests: drivers, orders, routes, zones | drivers/__tests__/*.test.ts, orders/__tests__/*.test.ts, routes/__tests__/*.test.ts, zones/__tests__/*.test.ts | ~3,200 | P0
PK (Sr. Backend) | Priya | Shopify app TODO fixes + shipping-profiles tests | shopify-app webhooks.tsx fixes (user ID mapping, shop config pickup, order DB fetch), shipping-profiles/__tests__/*.test.ts | ~1,800 | P0
AM (Integration) | Aisha | Core module tests: integrations, events, push, shops | integrations/__tests__/*.test.ts, events/__tests__/*.test.ts, push/__tests__/*.test.ts, shops/__tests__/*.test.ts | ~3,000 | P0
KS (QA Lead) | Kavitha | Core module tests: migration + E2E platform adapter flow test | migration/__tests__/*.test.ts, platforms/__tests__/e2e-platform-flow.test.ts (Shopify→WooCommerce→Magento→Custom full flow) | ~2,200 | P1
DM (Frontend) | Deepak | Tailwind Batch 19 (5 pages, 5+ styles) | admin/design-system, widgets, page.tsx (home), drivers, campaigns/[id] | ~600 | P1
NK (Frontend Lead) | Neha | Tailwind Batch 20 (5 pages, 5+ styles) | (auth)/layout, shipments, (auth)/register, admin/shops/[id], admin/page | ~500 | P1
VS (Component Dev) | Vikram | Tailwind Batch 21 (5 pages, 5+ styles) | activity, widget-config, routes/page, routes/[id], orders/local | ~500 | P1
SPRINT 3.7 TOTALS |  | Auth actions, 14 core module test suites, 4 Shopify TODO fixes, 15 Tailwind pages |  | ~15,000

## Sprint 3.8 Plan
Sprint 3.8 Plan — Error Boundaries, Security, Route Tests & Tailwind Final
Agent | Assignee | Task | Deliverables | Est. Lines | Priority
AR (CTO) | Arjun | ADR-018 Error Handling + .gitleaks.toml + Security Fix | ADR-018 error-handling-resilience.md, .gitleaks.toml config, fix sk_live/sk_test → sk_example in stores + api-keys pages | ~700 | P0
RG (Backend Lead) | Rohan | API route tests batch 1: auth, billing, campaigns | apps/api/src/routes/__tests__/auth.test.ts, billing.test.ts, campaigns.test.ts | ~3,000 | P0
SP (Full-stack) | Sanya | API route tests batch 2: shipments, collections, integrations | apps/api/src/routes/__tests__/shipments.test.ts, collections.test.ts, integrations.test.ts | ~3,000 | P0
PK (Sr. Backend) | Priya | API route tests batch 3: customers, payments, locations | apps/api/src/routes/__tests__/customers.test.ts, payments.test.ts, locations.test.ts | ~3,000 | P0
AM (Integration) | Aisha | API route tests batch 4: products, users, shops + webhook routes | apps/api/src/routes/__tests__/products.test.ts, users.test.ts, shops.test.ts | ~3,000 | P0
KS (QA Lead) | Kavitha | API route tests batch 5: analytics, admin, support-tickets | apps/api/src/routes/__tests__/analytics.test.ts, admin.test.ts, support-tickets.test.ts | ~3,000 | P0
DM (Frontend) | Deepak | Next.js error boundaries + loading states | error.tsx (root + per-route-group), loading.tsx (root + key pages), not-found.tsx, ErrorBoundary component | ~800 | P0
NK (Frontend Lead) | Neha | Tailwind Batch 22 (7 pages, 4-style tier) | settings, routes, routes/create, locations, delivery, calendar, (auth)/login → all ≤1 inline style | ~500 | P1
VS (Component Dev) | Vikram | Tailwind Batch 23 (7 pages, 3-style tier) + clean dist/ | zones, time-slots, shipping-profiles, orders, notifications, collections, billing → ≤1 inline style; remove tracked dist/ files | ~500 | P1
SPRINT 3.8 TOTALS |  | ADR-018, security fix, 15 API route test suites, error boundaries, 14 Tailwind pages, dist cleanup |  | ~17,500

## Sprint 3.9 Plan
Agent | Role | Task | Status | Files | Lines | Test Cases
AR | CTO | CONTRIBUTING.md + Docker Compose + Dockerfile | Done | 4 | 863 | -
RG | Backend Lead | Route tests batch 6: activity-logs, analytics-events, audit, carriers, tracking | Done | 5 | 3974 | 241
SP | Full-stack | Route tests batch 7: orgs, routes-api, permissions, time-slots, zones | Done | 5 | 3591 | 260
PK | Sr. Backend | Route tests batch 8: shipping-profiles, calendar-rules, notification-templates, messages, saved-views | Done | 5 | 4060 | 211
AM | Integration | Route tests batch 9: woocommerce-webhooks, magento-webhooks, custom-webhooks, outbound-webhooks, workflow-orders | Done | 5 | 4229 | 227
KS | QA Lead | Route tests batch 10: workflow-delivery, workflow-drivers, workflow-executions, pos, widget-config | Done | 5 | 4413 | 335
DM | Frontend | DatePicker + Pagination UI components | Done | 3 | 520 | -
NK | Frontend Lead | Tailwind Batch 24: widgets, drivers, campaigns/[id], design-system, register | Done | 5 | ~ | -
VS | Component Dev | Tailwind Batch 25: widget-config, admin, activity, analytics, integrations, admin/users, admin/customers | Done | 7 | ~ | -

## Sprint 4.0 Plan
Agent | Role | Task | Status | Files | Lines | Test Cases
AR | CTO | ADR-019 CI/CD + LICENSE + CI hardening | Done | 3 | 468 | -
RG | Backend Lead | Final 4 route tests: auth-providers, billing-subscriptions, feature-requests, payment-methods | Done | 4 | 3170 | 211
SP | Full-stack | Integration tests: order-lifecycle, auth-flow, billing-flow, webhook-chain | Done | 4 | 4001 | 87
PK | Sr. Backend | Shopify app tests: app-index, app-settings, app-webhooks, app-orders | Done | 4 | 3772 | 237
AM | Integration | Webhook E2E: Shopify, WooCommerce, Magento, cross-platform | Done | 4 | 3676 | 133
KS | QA Lead | Component unit tests: button, card, badge, input, modal, table, date-picker, pagination, error-boundary | Done | 9 | 4822 | 200+
DM | Frontend | 6 new UI components: Breadcrumb, Avatar, Switch, Checkbox, Alert, Progress | Done | 7 | 559 | -
NK | Frontend Lead | Tailwind Batch 26: drivers, widgets, campaigns/[id], design-system, register | Done | 5 | ~ | -
VS | Component Dev | Tailwind Batch 27: routes, locations, delivery, calendar, login, orders/local, routes/[id], routes/create | Done | 8 | ~ | -

## Sprint 4.1 Plan
Agent | Role | Task | Status | Deliverables
AR | CTO | ADR-020 docs architecture + Fumadocs scaffold + AI search config | Planned | ADR-020, apps/docs scaffold
RG | Backend Lead | API reference: OpenAPI spec cleanup + 73 endpoint doc pages | Planned | openapi.json, route docs
SP | Full-stack | Getting Started + Architecture + Self-Hosting guides (MDX) | Planned | 3 MDX guides, env ref
PK | Sr. Backend | SDK scaffold: packages/sdk auto-generated TypeScript client | Planned | packages/sdk package
AM | Integration | Platform adapter guides (Shopify/WooCommerce/Magento/Custom) | Planned | 4 platform MDX files
KS | QA Lead | Testing guide + Contributing guide + ADR browser section | Planned | Testing guide, ADR config
DM | Frontend | Docs theme: dark-first design, landing page, navigation, search | Planned | Custom theme, layout
NK | Frontend Lead | Component gallery: 23 components with live previews + props | Planned | 23 component pages
VS | Component Dev | Workflow engine + notification + billing/RBAC guides | Planned | 5+ MDX guide files

## Sprint 4.2 Plan
Sprint 4.2 — DX Polish, SDK Tests, Seed Data & Driver App Build-Out
Theme: Make the monorepo bootable, SDK production-ready, seed data for demo, driver app screens
Agent | Assignment | Deliverables | Skill(s)
AR - Aarav (CTO) | ADR-021 DX & Monorepo Bootability + turbo.json tuning | ADR-021 (~400 lines), updated turbo.json with proper pipeline (build/dev/lint/test/typecheck/db:generate), workspace package.json fixes, tsconfig references cleanup | system-design
RG - Raj (Backend Lead) | Database seed scripts + .env.example validation | packages/db/src/seed.ts (demo data: 3 orgs, 10 users, 50 orders, 20 drivers, 5 zones, sample shipments), seed command in package.json, .env.example audit with all required vars documented | system-design
PK - Priya (Sr. Backend) | SDK test suite + publish config | packages/sdk/__tests__/client.test.ts, orders.test.ts, drivers.test.ts, zones.test.ts, shipments.test.ts, errors.test.ts (~6 test files, 200+ cases), tsup.config.ts for build, package.json publish fields (main/module/types/exports) | testing-strategy
SP - Sanjay (Full-stack) | Driver app screens build-out | Enhanced HomeScreen (stats dashboard), ShipmentListScreen (filterable list with status badges), RouteDetailScreen (turn-by-turn with map placeholder), DeliveryProofScreen (camera + signature capture), shared hooks (useAuth, useApi, useLocation) | frontend-design
DM - Dev (Frontend) | Tracking page polish + live map | TrackingLandingPage redesign (order lookup), ShipmentTracker (status timeline + live map placeholder with Leaflet stub), DriverCard (ETA + driver info), responsive mobile-first layout, Tailwind + dark theme | frontend-design
NK - Neha (Frontend Lead) | Dashboard remaining gaps + settings page | Settings page (/settings with tabs: profile, organization, billing, integrations, API keys), Notification preferences page, Activity feed realtime indicator, remaining page polish (any pages missing loading/error states) | frontend-design
VS - Vikram (Component Dev) | New shared components + Storybook-style gallery page | FileUpload component, Combobox (searchable select), Timeline component, StatusBadge (delivery-specific), CommandPalette (CMD+K), update component index.ts exports, update docs gallery MDX for new components | frontend-design
KS - Kavitha (QA Lead) | SDK tests + docs app tests + smoke test script | apps/docs/__tests__/build.test.ts (docs build smoke), packages/sdk/__tests__/integration.test.ts (mock server E2E), scripts/smoke-test.sh (boots API, hits /health, verifies response), CI workflow update for smoke test step | testing-strategy
AM - Aisha (Integration) | Webhook delivery dashboard + integration health page | Dashboard /integrations/webhooks page (delivery log table, retry button, status indicators), /integrations/health page (integration status cards with last-check timestamps), API routes for webhook delivery history query | frontend-design

## Sprint 4.3 Plan
Sprint 4.3 — witylogix CLI Deployment Tool + AI Engineer Onboarding
Theme: One-line VM deployment, CLI subcommands, Caddy SSL, AI diagnostics, production Docker Compose
Agent | Assignment | Deliverables | Skill(s)
AR - Aarav (CTO) | ADR-022 CLI Architecture + main entrypoint | docs/adr/ADR-022-cli-deployment-tool.md (~500 lines), infra/cli/witylogix (main script ~300 lines with subcommand routing, help, version, color output, config loader) | system-design
RG - Raj (Backend) | deploy + install subcommands | infra/cli/commands/install.sh (~200 lines — Docker bootstrap, dir creation, image pull), infra/cli/commands/deploy.sh (~300 lines — build/pull, migrate, seed, start, health wait, zero-downtime detection) | system-design
PK - Priya (Sr. Backend) | backup + restore + upgrade subcommands | infra/cli/commands/backup.sh (~200 lines — pg_dump with compression, S3 upload optional, rotation), infra/cli/commands/restore.sh (~150 lines), infra/cli/commands/upgrade.sh (~200 lines — pull, migrate, rolling restart) | system-design
SP - Sanjay (Full-stack) | ssl + env subcommands | infra/cli/commands/ssl.sh (~200 lines — Caddy config generator, domain setup, cert check), infra/cli/commands/env.sh (~250 lines — interactive .env configurator, validation, secret generation) | system-design
ZR - Zara (AI Engineer) | ai setup + ai diagnose subcommands | infra/cli/commands/ai.sh (~300 lines — Claude API key config, log collector, diagnostic prompt builder, structured output parser), infra/cli/templates/ai-diagnose-prompt.txt | system-design
NK - Neha (Frontend Lead) | dev subcommand | infra/cli/commands/dev.sh (~250 lines — dependency checker, port allocator, env validator, turbo boot with status table, process manager, graceful shutdown handler) | system-design
DM - Dev (Frontend) | status + doctor subcommands | infra/cli/commands/status.sh (~200 lines — HTTP probes for all services, formatted table), infra/cli/commands/doctor.sh (~250 lines — disk/mem/ports/DNS/Docker/connectivity checks, report generator) | system-design
KS - Kavitha (QA Lead) | CLI tests + init subcommand | infra/cli/commands/init.sh (~200 lines — contributor setup, deps install, prisma generate, seed, smoke test), infra/cli/__tests__/test-cli.sh (~300 lines — test harness for all subcommands), CI workflow update | testing-strategy
VS - Vikram (Component) | logs + scale + destroy subcommands | infra/cli/commands/logs.sh (~150 lines — multi-service log tailing with color), infra/cli/commands/scale.sh (~100 lines — Docker Compose scale wrapper), infra/cli/commands/destroy.sh (~120 lines — clean teardown with confirmation) | system-design
AM - Aisha (Integration) | Caddy templates + production Docker Compose | infra/cli/templates/Caddyfile (~80 lines — reverse proxy for api/app/docs with auto-SSL), infra/docker-compose.prod.yml (~200 lines — production-grade with healthchecks, restart policies, resource limits, Caddy service), infra/cli/templates/env.template | system-design

## Sprint 4.4 Plan
Sprint 4.4 — E2E Testing, Event Bus, Platform Admin & Gap Closure
Planned: 2026-03-10 ¦ Focus: E2E framework, event bus, platform admin, package maturity
Agent | Role | Deliverable | Files (est) | Lines (est) | Status
AR (Arjun) | CTO / Architect | ADR-023 E2E Testing & Event Bus architecture; Prisma schema additions (authProvider, authSession, platformAdmin, posConfig models) | 3 | ~900 | PLANNED
RG (Rohan) | Backend Lead | Event Bus with Redis Streams — typed event emitter, pub/sub, event store, replay, dead letter queue | 8 | ~2,400 | PLANNED
PK (Priya) | Sr. Backend | Auth provider registry core module — provider CRUD, session management, token validation, multi-tenant | 6 | ~1,800 | PLANNED
SP (Sanya) | Full-stack | Workflow integration triggers — auto-trigger workflows from order/shipment/driver API endpoints + Socket.io events | 5 | ~1,500 | PLANNED
ZR (Zara) | AI Engineer | AI-powered monitoring — anomaly detection for delivery SLAs, predictive ETA model, alert recommendations engine | 6 | ~2,000 | PLANNED
NK (Neha) | Frontend Lead | Activity log redesign — real-time filterable event stream page with timeline view, user actions, system events | 3 | ~900 | PLANNED
DM (Dhruv) | Frontend | Design tokens page — interactive token reference (colors, spacing, typography, shadows) + shadcn/ui component preview gallery | 3 | ~1,100 | PLANNED
VS (Vikram) | Component Dev | Package maturity — add build scripts (tsup) + test scripts to framework, types, validators, workflows packages; fix exports | 12 | ~1,600 | PLANNED
KS (Kavitha) | QA Lead | E2E test framework — Playwright setup, page objects, 5 critical flow tests (auth, order CRUD, driver assign, tracking, webhooks) | 10 | ~3,000 | PLANNED
AM (Aisha) | Integration | Webhook management page redesign + event log viewer page + Shopify workflow bridge (order webhook → workflow trigger) | 5 | ~1,800 | PLANNED
TOTALS |  |  | ~61 files | ~17,000 lines

## Sprint 4.5 Plan (Done)
Agent | Role | Sprint 4.5 Task | Files/Packages | Key Deliverables | Competitive Benchmark | Status
AR | CTO / Architect | Route Timeline Dispatcher Dashboard (Routific-quality) | apps/dashboard/src/app/(dashboard)/dispatch/, packages/core/src/dispatch/ | Map with color-coded driver routes + timeline view (8am-7pm). Unscheduled/Scheduled toggle. Drag-and-drop route editing. Real-time stats bar (drivers, stops, km, time). | Routific: 10 color-coded routes, 540 stops, timeline per driver | PLANNED
NK | Frontend Lead | Checkout Date/Time Picker Widget (Pickeasy-quality) | packages/checkout-widget/, extensions/checkout-ui/ | Embeddable widget: date calendar, time slot grid with capacity indicators, zone-based rate display, blackout dates, cut-off times, zipcode validation, prep time settings. | Pickeasy: 8K merchants, slot limits, blackout, zip validation, $9.99-49.99 | PLANNED
DM | Frontend Dev | Customer Self-Service Portal | apps/customer-portal/ | Next.js portal: order history with timeline, live tracking, rescheduling flow, delivery preferences (safe place, instructions), driver ratings, notification preferences. | Route4Me: only platform with self-service portal. First-mover for open-source | PLANNED
RG | Backend Lead | Slot Engine API & Capacity Management | packages/core/src/slots/, apps/api/src/routes/checkout/ | Slot availability API, capacity limits per slot/day, zone-rate calculator, order deadline engine (e.g. Friday pickup by Thu 4pm), cart integration endpoints. | Pickeasy: order deadlines, daily limits, product-specific slots | PLANNED
PK | Sr. Backend | POD v2: Photo + Signature + QR + Status Timeline | packages/core/src/pod/, apps/api/src/routes/pod/ | Multi-method POD: photo capture, e-signature pad, QR/barcode scan. Delivery status timeline (Planned → Out for Delivery → Delivered + photo). S3/R2 storage. | Routific: status timeline with photo. Fleetbase: QR+signature+manual | PLANNED
SP | Full-stack | Customer Notification Engine v2 + SMS/WhatsApp | packages/core/src/notifications-v2/, apps/api/src/routes/notifications/ | Multi-channel: email + SMS (Twilio) + WhatsApp (Meta Business) + push. Template engine. SMS with tracking link + time window (Routific pattern). Delivery webhooks. | Routific: SMS with tracking link + time window. ScrollEngine: WhatsApp | PLANNED
VS | Component Dev | Checkout & Dispatch Component Library | packages/checkout-widget/src/, apps/dashboard/src/components/dispatch/ | Checkout: DatePicker, TimeSlotGrid, ZoneMap, DeliveryOptions, AddressAutocomplete. Dispatch: RouteTimeline, DriverCard, StopMarker, StatsBanner. | Routific timeline + Pickeasy checkout as UX reference | PLANNED
KS | QA Lead | E2E: Dispatch, Checkout & Customer Portal | tests/e2e/specs/dispatch/, tests/e2e/specs/checkout/, tests/e2e/specs/portal/ | Playwright suites: dispatch timeline interaction, checkout widget slot selection, customer portal auth + reschedule, POD photo upload, SMS notification delivery. | Full coverage for all Sprint 4.5 customer-facing features | PLANNED
AM | Integration | Shopify Checkout Extension + Google Maps/Calendar | extensions/checkout-ui/, packages/core/src/integrations/google/ | Shopify checkout extension with embedded date/time widget. Google Maps for zone visualization. Google Calendar sync for merchant order reminders. | Pickeasy: Google Maps + Calendar. Zapiet: Shopify certified | PLANNED
ZR | AI Engineer | Smart Slot Recommendation + ML ETA Engine | packages/core/src/ai-slots/, packages/core/src/ai-eta/ | ML slot recommender: demand prediction, driver availability forecast. Traffic-aware ETA model (start with 3-5 models, target Routific's 179 as long-term goal). | Routific: 179 ML models. Nobody has AI slot recommendation — first-mover | PLANNED
THEME | Sprint 4.5: Customer Experience & Checkout Enhancement — Routific-quality dispatcher dashboard, Pickeasy-quality checkout widget, customer self-service portal, POD v2 with status timeline, SMS/WhatsApp notifications, AI slot recommendation engine.
BENCHMARKS | UX: Routific dispatcher timeline + driver app + POD flow + SMS tracking. Checkout: Pickeasy date/time picker + slot capacity + blackout + zip validation. Portal: Route4Me self-service. Notifications: Routific SMS + ScrollEngine WhatsApp.

## Sprint 4.7 Plan (Done)
Sprint 4.7 — Telematics, Traffic-Aware ETA & Integration Ecosystem
Agent | Role | Task | Files/Packages | Key Deliverables | Gap Ref | Status
AR - Arjun | CTO | Telematics Architecture ADR-026 + Fleet Dashboard | docs/adr/, apps/dashboard/src/app/(dashboard)/fleet/ | ADR-026 telematics gateway; Fleet dashboard page with vehicle status, fuel, diagnostics; Fleet overview API endpoints | G-11 | ⬜
DM - Deepak | Frontend | Courier Partner Directory UI + Partner Onboarding | apps/dashboard/src/app/(dashboard)/partners/ | Partner directory page with search/filter, partner detail cards, onboarding wizard (3-step), courier comparison view, partner settings | G-14 | ⬜
NK - Nikhil | Frontend Lead | Fleet Map & Telematics Dashboard Components | apps/dashboard/src/components/fleet/ | Vehicle tracker map (real-time positions), fuel gauge widget, diagnostic alerts panel, driver behavior heatmap, idle time chart, fleet stats cards | G-11 | ⬜
RG - Rahul | Backend Lead | Telematics Adapter Layer (Samsara + Geotab) | packages/core/src/integrations/telematics/ | TelematicsAdapter interface, Samsara client (REST API v1), Geotab client (MyGeotab), vehicle position/fuel/diagnostics polling, event webhooks, rate limiting | G-11 | ⬜
SP - Sanjay | Full-stack | Invoice Completion + QuickBooks/Xero Integration | packages/core/src/invoicing/, packages/core/src/integrations/accounting/ | Configurable billing rules (per-delivery/mile/hour/subscription), email invoice delivery, QuickBooks OAuth2 adapter, Xero OAuth2 adapter, accounting sync API | G-13 | ⬜
VS - Vikram | Component Dev | Fleet & Partner UI Components + Courier Cards | apps/dashboard/src/components/fleet/, apps/dashboard/src/components/partners/ | Vehicle status card, fuel gauge (SVG), diagnostic badge, speed chart, courier partner card, rate comparison table, partner badge, SLA indicator | G-11, G-14 | ⬜
PK - Priya | Sr. Backend | Courier Partner Adapters (Onfleet, Stuart, Uber Direct) | packages/core/src/integrations/couriers/ | CourierAdapter interface, Onfleet client (Tasks API), Stuart client (Jobs API), Uber Direct client (Deliveries API), rate quotes, dispatch, tracking, webhook handlers | G-14 | ⬜
KS - Kavitha | QA Lead | Telematics + Courier + Invoice Integration Tests | tests/integration/telematics/, tests/integration/couriers/, tests/integration/invoicing/ | Samsara adapter tests, Geotab adapter tests, Onfleet/Stuart/Uber Direct tests, invoice billing rules tests, QuickBooks/Xero sync tests, 200+ test cases | G-11, G-13, G-14 | ⬜
AM - Aisha | Integration | Traffic-Aware ETA v2 + Google Directions Integration | packages/core/src/ai-eta-v2/, packages/core/src/integrations/traffic/ | Google Directions API client (distance matrix, traffic data), TomTom Traffic API adapter, traffic-aware routing, ETA adjustment pipeline, real-time traffic overlay API | G-12 | ⬜
ZR - Zara | AI Engineer | ML ETA Engine v2 — Traffic-Aware Multi-Model | packages/core/src/ai-eta-v2/ | Traffic zone classifier, time-of-day model, day-of-week model, distance-decay model, historical delivery model, weather impact model, ensemble with confidence intervals, auto-calibration, model performance tracker | G-12 | ⬜

## Sprint 4.8 Plan
Agent | Role | Task | Deliverables | Est. Lines | Status
AR - Arjun | CTO | ADR-027 AI Demand Prediction Architecture + Platform Health Dashboard | ADR-027 doc, demand-prediction types, platform health page, system status API | 3000 | Planned
DM - Deepak | Frontend | Invoice Management Dashboard + Payment Tracking UI | Invoice list page, invoice detail, payment history, invoice PDF preview component | 2500 | Planned
NK - Nikhil | Frontend Lead | Courier Live Tracking Map + Dispatch Console | Live courier map, dispatch console, courier assignment panel, delivery timeline | 2400 | Planned
RG - Rahul | Backend Lead | Courier Webhook Handlers + Partner Rating Engine | Webhook processors for Onfleet/Stuart/Uber, partner rating service, SLA tracker | 3500 | Planned
SP - Sanjay | Full-stack | Invoice PDF Generation + Payment Gateway Integration | PDF invoice generator (html-pdf), Stripe payment links, payment reconciliation | 4000 | Planned
VS - Vikram | Component Dev | Invoice & Payment UI Components + Courier Tracking Cards | Invoice table, payment status badge, amount display, courier tracking card, delivery ETA card | 2800 | Planned
PK - Priya | Sr. Backend | Courier Partner Rating + Multi-Courier Routing Engine | Partner performance scoring, auto-courier selection v2, cost optimization, SLA enforcement | 3800 | Planned
KS - Kavitha | QA Lead | Invoice + Payment + Courier Dispatch Integration Tests | Invoice generation tests, payment flow tests, courier dispatch tests, webhook handler tests | 2000 | Planned
AM - Aisha | Integration | AI Demand Prediction Data Pipeline + Feature Store | Historical delivery aggregator, time-series feature extractor, demand forecasting pipeline | 4500 | Planned
ZR - Zara | AI Engineer | AI Demand Prediction Models + Smart Scheduling Engine | Demand forecasting models (ARIMA-like, seasonal decomposition, zone clustering), smart slot optimizer | 5500 | Planned